SCALING INTELLIGENCE OPERATING SYSTEM

Integrated Assessment & Richard Kohl Coaching Preparation

Solution Track: Bundled Digital Financial Services — Kenya & India

CGIAR Scaling for Impact (S4I) · Area of Work 2

How to read this report This is a blind, evidence-based assessment. Its purpose is not to confirm scaling readiness but to determine what is proven, what remains assumption, and what the most upstream constraint is. Three disciplines were applied collaboratively — Librarian (what is known), Analyst (what it means), and Strategy Coach (Kohl-style systems reasoning). Where they disagree, the disagreement is preserved. Every substantive line is tagged: EVIDENCE · INTERPRETATION · JUDGEMENT · RECOMMENDATION · UNKNOWN.

Evidence base reviewed

- Expression of Interest (EoI) — Scaling bundled DFS, incl. two Letters of Support (Dvara 19 Sep 2025; ACRE, undated)

- Solution Track Profile v1.0 (Feb 2026; reviewed 27/05/2026)

- Inception meeting deck (10 Jan 2026), meeting minutes (16 Jan 2026), and full meeting transcript (16 Jan 2026)

- Cited-but-unsupplied: 6 academic papers/discussion papers; TAAT catalogue entry; several media links

Status: Working analysis — not yet reviewed into the repository.

# Contents

Contents	2

1 · Executive Summary	4

2 · Scaling Knowledge Summary	5

2.1 Key knowledge objects & provenance	5

2.2 Document assertion vs. observed evidence	5

2.3 Cross-document inconsistencies (must-resolve)	5

2.4 Cited-but-unsupplied & evidence gaps	6

2.5 Recommended Knowledge Cards	6

3 · Scaling Intelligence Assessment	7

3.1 Ambition, denominator & theory of scaling	7

3.2 Innovation package & adoptability	7

3.3 Actor map & incentive structure (scaling-system map)	7

3.4 Demand analysis — five distinct demands	7

3.5 Delivery, financing, institutional ownership, policy	8

3.6 Additionality test (S4I vs. existing platform)	8

3.7 Weakest-link analysis	9

3.8 Critical assumptions	10

3.9 Sustainability analysis	10

3.10 Evidence quality & confidence	10

4 · Stage-Gating Assessment	12

4.1 Component-level staging	12

4.2 Entry / exit criteria & gaps	12

4.3 Integrated judgement	12

5 · Scaling Strategy Review	13

5.1 Strategic diagnosis	13

5.2 Priority actions	13

5.3 Owner-specific recommendations	13

5.4 Adaptive management (decision rules, not fixed plans)	13

5.5 Institutionalization assessment	14

5.6 Learning experiments	14

6 · Richard Kohl Coaching Preparation Brief	15

6.1 Executive coaching summary	15

6.2 Five questions Richard is most likely to ask	15

6.3 Five assumptions he is most likely to challenge	15

6.4 Three areas where the team is likely overestimating readiness	15

6.5 Three strengths Richard is likely to recognize	15

6.6 Evidence the team should have available	16

6.7 Evidence currently missing	16

6.8 Recommended 90-minute coaching agenda	16

6.9 Three conversations the team should have internally first	16

6.10 If Richard remembered only one thing six months later	16

7 · Operating System Improvement Recommendations	17

7.1 By component	17

7.2 Highest-value OS change	17

7.3 Assessor's provenance note	17

# 1 · Executive Summary

Executive judgement (Strategy Coach, Kohl-style) Stage-gate classification: Transition to Scale — with a targeted bottleneck condition. One-sentence rationale: The innovation is technically validated and commercially live at small scale, but the scaling ambition (100,000 farmers) depends on an unproven insurance risk-diversification and subsidy-financing pathway that no supplied evidence addresses. Main weakest link: Financing sustainability of the insurance leg at scale — specifically, who pays for customer acquisition and subsidies on the journey from ~15,000 to hundreds of thousands of farmers, and whether the insurance pool ever reaches viable risk diversification.

### What is genuinely proven

EVIDENCE  RCTs with ~5,000 farmers in India (Odisha, 2 states) and Kenya (7 counties) show the product works for end-users: +20 pp formal credit use (India), +20% insurance take-up and +10 pp fertilizer use (Kenya), +~US$250 household agricultural income, and improved women's empowerment / lower stress. Innovation Readiness = 9, Use = 9.

EVIDENCE  Two enterprises are already operating commercially: Dvara is lending to 15,000 farmers via KhetScore (EoI text also says 23,000 in one place — see inconsistency log); ACRE has placed PBI products commercially via TARA.

### What remains assumption

INTERPRETATION  The evidence proves problem–solution fit and adoptability, not scaling-system viability. Kohl's core distinction — technical effectiveness ≠ scaling readiness — is the central tension in this track.

UNKNOWN  No supplied document contains evidence on (a) the minimum pool size for insurance viability, (b) the source and quantity of subsidy/FLDG financing beyond 2026, (c) claims-settlement speed relative to the planting cycle, or (d) how climate risk is priced when historical series are no longer predictive.

### The three headline messages

- The track is a strong Transition-to-Scale case, not yet an active-scaling case. Treat the 100,000-farmer figure as an ambition, not a validated trajectory.

- The binding constraint is upstream and financial, not delivery or demand. Richard Kohl already signalled this in the 16 Jan meeting via the Syngenta Foundation precedent.

- The most valuable near-term move is a set of small, decisive learning experiments (insurance-viability math, claims-speed data, subsidy-exit test) that could resolve the largest uncertainties at low cost before further investment.

# 2 · Scaling Knowledge Summary

Discipline lead: Scaling Librarian. This section organises what the evidence base contains, preserves provenance, and separates document assertions from observed evidence. It makes no strategic judgement.

## 2.1 Key knowledge objects & provenance

| Knowledge object | Source (provenance) | Evidence type | Note |
| --- | --- | --- | --- |
| Bundled credit + PBI product | EoI §1; Profile §2; deck s2 | Innovation description | Consistent across sources |
| RCT impact results (India) | Kramer et al. 2024 IFPRI DP2288; 2025 AAEA paper | Independently designed RCT | Papers cited, not supplied |
| RCT impact results (Kenya) | Kramer et al. 2023, 2024 AAEA papers | RCT / experimental | Papers cited, not supplied |
| Readiness score 9 / Use score 9 | EoI §3 annex (screenshots) | Self-assessment (IPSR calculator) | Participant self-report, not third-party |
| Commercial traction (Dvara 15k; ACRE via NCBA/SBM) | EoI §2/§3; LoS Dvara | Partner assertion / monitoring | Numbers vary by document |
| Business-model unit economics | EoI §2 (cost/revenue %) | Partner-reported figures | Not independently audited |
| Scaling targets & timeline | EoI §3; Profile §2; deck s7 | Plan / projection | Revised down 100k→15k for 2026 |
| Partner commitments | LoS Dvara (19/9/25), LoS ACRE (undated) | Letters of support | Endorsement, not binding co-investment |

## 2.2 Document assertion vs. observed evidence

EVIDENCE  Observed (in-hand): the EoI, Profile, deck, minutes and transcript — these are primary S4I documents actually supplied and readable.

INTERPRETATION  Asserted-but-unobserved: all six RCT/impact papers are cited but not supplied. The impact claims that anchor the entire readiness case therefore rest on assertions the assessor cannot verify against source. This is the single largest provenance gap.

## 2.3 Cross-document inconsistencies (must-resolve)

| Item | Conflict | Where |
| --- | --- | --- |
| Dvara reach | "15,000 farmers" vs. "KhetScore to 23,000 farmers" vs. "lending to 15,000" | EoI §2 (Evidence of Impact) vs. EoI §2 (Scaling Pathway) vs. §3 |
| 2026 farmer target | "25,000" (EoI timeline) vs. "15,000" (Profile, deck, transcript — revised down) | EoI §3 timeline vs. Profile §2 / deck s3 |
| Insurers named | "Tata AIG" (Profile) vs. "HDFC Ergo" (EoI) for India; "APA/Britam" consistent for Kenya | Profile §4 vs. EoI §2 |
| Bilateral funder (ACRE) | "Ministry of Foreign Affairs, France" (transcript) vs. "FEXTE" (deck) | Transcript vs. deck s7 |
| Loan interest economics | India interest = 10% of loan value (deck) but EoI lists interest 10% + FPO services 5% | Deck s6 vs. EoI §2 |
| Scaling ambition denominator | "100,000 farmers" (headline) vs. 15k+30k+45k = 90,000 (timeline math) | EoI/Profile vs. summed annual targets |

RECOMMENDATION  Create a single Reconciled Facts Knowledge Card that fixes canonical values for reach, targets, partners, and unit economics before any external communication or investor engagement.

## 2.4 Cited-but-unsupplied & evidence gaps

- All 6 academic references (Ceballos 2019; Kramer 2021, 2023, 2024×2, 2025) — acquire and create Evidence Records

- Partner contracts / commercial terms (repeatedly requested by S4I in the meeting) — not supplied

- Insurance actuarial / pool-viability analysis — does not appear to exist in the evidence base

- Claims-settlement speed data — flagged by Kohl and Krupnik; not supplied

- Subsidy phase-out financing plan beyond 2026 — not supplied

- Disadoption / renewal (persistency) data — acknowledged as unknown by the team

## 2.5 Recommended Knowledge Cards

- Card: "Picture-Based Insurance + Digital Credit Bundle" (concept + evidence record)

- Card: "Insurance pool viability at scale" (open-question / heuristic — links to Syngenta Foundation precedent)

- Card: "Agent network as delivery black box" (cross-cutting delivery heuristic; recurs in other S4I tracks)

# 3 · Scaling Intelligence Assessment

Discipline leads: Scaling Analyst + Strategy Coach.

## 3.1 Ambition, denominator & theory of scaling

EVIDENCE  Ambition: 100,000 farmers across Kenya & India by 2028 (≥50% women, ≥25% youth, 5% marginalised); US$25m disbursed/insured; 100,000 ha. 2026 milestone revised to 15,000 farmers, US$6m (finance target held).

INTERPRETATION  Denominator discipline is weak. The 100,000 figure is a target, not a defined addressable market. The summed annual targets (90,000) do not reconcile to the headline, and no document defines the total population of collateral-constrained smallholders the model could serve.

JUDGEMENT  Theory of scaling = private-sector, market-systems, "crowd-in": S4I catalytic funds strengthen tech + capacity + evidence → partners attract more financial institutions and bilateral finance → commercial growth continues after S4I. This is a coherent theory, but its load-bearing assumption (commercial self-sustainability of the insurance leg) is exactly the one with no supplied evidence.

## 3.2 Innovation package & adoptability

EVIDENCE  Package = digital credit-scoring (KhetScore/TARA) + picture-based multi-peril insurance + agent onboarding + capacity building + (in India) FPO aggregation. Accessible to non-smartphone users via agents.

JUDGEMENT  Adoptability is well supported. Bundling insurance with credit is a genuinely clever design move: it solves insurance's adverse-selection and demand problems by attaching insurance to something farmers actively want (a loan). This is the track's strongest strategic feature.

## 3.3 Actor map & incentive structure (scaling-system map)

| Function | Actor | Incentive | Risk |
| --- | --- | --- | --- |
| Demand creation | Agents + aggregators (MFIs/FPOs) | Medium | Agent incentives/biases a "black box" (team's own words); may cream-skim best farmers |
| Delivery | Dvara (lends directly); ACRE (via lenders) | Strong | Two different models; Kenya slower as it works through partners |
| Financing (credit) | MFIs, banks, social investors | Strong | Works where climate risk can be priced; capital exists |
| Financing (insurance pool) | Insurers (APA, Britam, HDFC/Tata AIG); reinsurer Zep-Re | Weak/unproven | Viability needs 0.5–1m farmers (Syngenta precedent); no pool math supplied |
| Subsidy / de-risking | S4I + "to-be-found" bilaterals | Weak | Who funds subsidies/FLDGs at 100k+ scale is unknown |
| Coordination | IFPRI + Alliance (CGIAR) | Medium | CGIAR role is catalytic/temporary by design — exit risk |
| Policy support | Ministries of Ag (not engaged) | Deferred | Deliberately deferred; may cap ceiling of private-only pathway |
| Learning/adaptation | CGIAR MELIA + AoW5 | Strong | Embedded MELIA is a genuine strength |

## 3.4 Demand analysis — five distinct demands

RECOMMENDATION  Kohl's method requires not assuming one demand implies another. They must be separated:

| Demand type | Evidence status | Verdict |
| --- | --- | --- |
| User (farmer) | RCT-validated; especially strong among women | Well supported |
| Market (aggregators) | Plausible revenue logic (input sales, farmer welfare); not measured | Emerging |
| Payer (who funds subsidies) | No committed source beyond 2026 | Insufficient |
| Institutional (lenders/insurers) | Some lenders requesting tool (NCBA, SBM); insurers place product | Emerging |
| Policy | Not engaged by design | Unknown / deferred |

JUDGEMENT  Strong user demand is being used, implicitly, to stand in for payer demand. It cannot. The farmer wants the loan; the farmer does not want to fund a national subsidy programme. This conflation is the demand-side face of the weakest link.

## 3.5 Delivery, financing, institutional ownership, policy

EVIDENCE  Delivery is via existing commercial operations of two established enterprises — a real asset. Financing of the credit leg is described as revenue-positive (India: 10% interest + 5% FPO svc vs. 7% opex + 5% risk capital).

INTERPRETATION  Institutional ownership is strong for the enterprises, weak for the public good. Dvara and ACRE will own and continue the commercial product; but the inclusive-scaling objective (women/youth/marginalised, non-title farmers) is only protected while subsidies and CGIAR MELIA persist.

## 3.6 Additionality test (S4I vs. existing platform)

| Do not let the platform's proof validate the S4I increment This is the discipline the prompt insists on. The existing platforms (KhetScore, TARA) are proven; the S4I additionality is a separate, less-proven thing. |  |  |  |
| --- | --- | --- | --- |
| Layer |  | What it is | Evidence status |
| Already proven |  | PBI concept; credit-scoring without collateral; commercial operation at ~15k; farmer-level impact | Well supported (RCTs + live operations) |
| New under S4I |  | (a) refined computer-vision loss models; (b) forward-looking climate-risk integration; (c) inclusive-outreach training; (d) crowd-in of new FIs & bilaterals; (e) MELIA on trust/disadoption | Emerging / unproven — this is the increment being funded |
| Evidence that applies ONLY to the platform |  | All RCT impact numbers; readiness score 9; commercial traction | Must not be cited as proof the S4I increment will work |
| Evidence supporting S4I additionality specifically |  | That catalytic funds will crowd in the financing needed for 100k scale | None supplied — this is the additionality gap |

JUDGEMENT  The additionality story is "acceleration + inclusion + evidence", which is legitimate. But the EoI at times uses platform proof (readiness 9, 15k farmers) to imply the 100k trajectory is proven. It is not. The additionality is a bet on crowding-in, and that bet is currently unevidenced.

## 3.7 Weakest-link analysis

Candidate weakest links were evaluated against the ambition. Each is assessed for whether it is upstream (causal, dominates others) or downstream (symptom).

| Candidate | U/D | Could bind? | Reasoning |
| --- | --- | --- | --- |
| Insurance pool viability & subsidy financing at scale | Upstream | Yes — dominant | If pools never reach viable diversification (0.5–1m precedent) and no one funds acquisition/subsidy from 15k→500k, the model cannot reach ambition regardless of delivery quality. Who pays, who continues after donor exit — both unanswered. |
| Agent incentives / delivery black box | Mid-stream | Yes | Determines inclusion and quality; but is a delivery-optimisation problem downstream of whether the financial model exists to deliver at all. |
| Climate-risk pricing under non-stationarity | Upstream | Yes | Genuinely upstream and unsolved industry-wide; but partners can price conservatively / use reinsurance — it raises cost rather than blocking existence. Feeds into the financing constraint. |
| Claims-settlement speed vs. planting cycle | Downstream | Yes | Breaks trust and persistency if slow; important but a fixable operational parameter, not a system-level blocker. |
| Farmer trust / persistency (disadoption) | Downstream | Yes | Symptom of claims speed + tangible-value perception; Kohl's Syngenta point about farmers quitting when no payout arrives. |
| Denominator / ambition definition | Upstream | Partly | A reasoning weakness rather than a field constraint; it hides the financing gap but doesn't itself block scale. |

### Anti-legibility check

INTERPRETATION  The most legible candidate — agent training / capacity building — is the one the workplan most emphasises, because it is fundable, schedulable and reportable. The anti-legibility check flags exactly this: the track may be gravitating to the visible, tractable constraint (train agents) while the illegible, harder constraint (a financing pathway that doesn't yet exist for the insurance leg at scale) receives least attention.

### Selected weakest link

The single most upstream constraint Financing sustainability of the insurance leg at scale Specifically: (1) whether the insurance pool can ever reach viable risk diversification at the numbers this model can plausibly reach, and (2) who funds customer acquisition, smart subsidies and FLDGs on the path from ~15,000 to hundreds of thousands of farmers. It dominates because every other function (delivery, demand, trust, inclusion) is contingent on the financial model existing at scale. Delivery quality is worthless if there is no viable pool to deliver into; trust is moot if the product is withdrawn when subsidies end. The Syngenta Foundation precedent — a well-funded insurance-scaling effort that could not cross this exact gap — is the reference case.

### Preserved disagreement between disciplines

INTERPRETATION  The CGIAR Scaling Coach and the Kohl Strategy Coach do not fully agree on the weakest link, and this is preserved rather than resolved:

- Kohl view (adopted as primary): the financing/pool-viability constraint is binding and upstream — consistent with his live meeting comments.

- CGIAR-coach view (minority): the agent-network delivery black box is the more actionable binding constraint for inclusive scaling in the 2026 horizon, because it is what determines whether the women/youth/marginalised targets are met at all. Under this view, financing is a 2027+ problem and agents are the 2026 problem.

JUDGEMENT  Both can be true at different time-horizons. Recommendation resolves the tension by sequencing: treat financing as the strategic gate and agents as the operational focus — not by declaring one wrong.

## 3.8 Critical assumptions

| Assumption | Evidence | Risk if wrong |
| --- | --- | --- |
| Bundling with credit makes the insurance pool viable at reachable numbers | Asserted; no pool math | Whole scaling model fails — reverts to Syngenta outcome |
| Subsidies/FLDGs can be phased out without collapsing uptake | Kenya plan: 20%→lower→0 over 3 yrs; untested | Uptake collapses at phase-out; not self-sustaining |
| Bilateral/social finance will crowd in to fund the 15k→100k gap | Several applications pending, none secured | Growth stalls at commercial-only trajectory |
| Climate risk can be priced adequately despite non-stationarity | Partners "doing what they can" | Mispriced risk → insurer losses → withdrawal |
| Claims settle fast enough for next planting cycle | No data; M-Pesa assumed to help | Trust erodes; persistency falls; disadoption |
| Agents deliver inclusively rather than cream-skimming | Acknowledged black box | Inclusion targets (women/youth/marginalised) missed |

## 3.9 Sustainability analysis

| Dimension | Rating | Basis |
| --- | --- | --- |
| Technical | Strong | Platforms operational; models being improved; readiness 9 |
| Financial (credit) | Moderate | Revenue-positive unit economics reported (unaudited) |
| Financial (insurance) | Weak | Pool viability unproven; subsidy dependence beyond 2026 |
| Institutional | Moderate | Enterprises will continue commercially; inclusive mandate less durable |
| Ownership | Strong | Private partners own product; CGIAR role explicitly temporary |
| Incentive | Moderate | Aligned for profitable segments; misaligned for hardest-to-reach |
| Political | Unknown | Policy engagement deferred; ceiling of private-only pathway untested |

## 3.10 Evidence quality & confidence

JUDGEMENT  Overall evidence quality: high for farmer-level impact, low for scaling-system viability. The RCT base is genuinely strong (multiple studies, two geographies, independent academic framing) — but every study addresses whether the product helps farmers, none addresses whether the system scales. Source independence is moderate: most studies share the same PI (Kramer/IFPRI), so they are not fully independent corroboration.

Confidence summary (Analyst scale) Problem–solution fit: Well supported Adoptability & user demand: Well supported Commercial viability of credit leg: Moderately supported Scaling-system viability (insurance + subsidy): Insufficient evidence Path to 100,000 farmers: Speculative

# 4 · Stage-Gating Assessment

Components are assessed separately because they sit at different stages, then integrated. "Component" here = the two legs of the bundle plus the inclusive-scaling wrapper.

## 4.1 Component-level staging

| Component | Current stage | Confidence | Basis |
| --- | --- | --- | --- |
| Digital credit (KhetScore, India) | Scaling | Moderate | Live commercial lending; revenue-positive; RCT-validated |
| Credit via lenders (TARA, Kenya) | Transition to Scale | Moderate | Works through partners; slower to materialise (3k vs 12k) |
| Picture-based insurance (both) | Transition to Scale | Low–Mod | Placed commercially but pool viability at scale unproven |
| Inclusive-scaling wrapper (women/youth/marginalised) | Proof of Concept | Low | Targets set; delivery via unproven agent-inclusion mechanism |

## 4.2 Entry / exit criteria & gaps

### Proof of Concept

- Entry: technical feasibility + problem fit. Met.

- Exit: validated impact under real-world conditions. Met (RCTs, readiness 9).

### Transition to Scale

- Entry: proven product + committed delivery partners + early commercial operation. Met.

- Exit: demonstrated business-model viability at scale + secured financing pathway + evidence of self-sustaining demand after subsidy. Not met.

- Remaining gaps: insurance-pool math; subsidy-exit evidence; crowd-in of committed finance; claims-speed data; agent-inclusion proof.

### Scaling

- Entry: viability + financing + institutional ownership demonstrated. Not met for the bundle as a whole (met for India credit leg alone).

## 4.3 Integrated judgement

Recommended gate Current integrated stage: Transition to Scale Recommended gate decision: ADVANCE with conditions (Targeted Bottleneck Support), NOT unconditional scaling investment. Confidence: Moderate. Justification: Advancing is justified by strong impact evidence and live commercial operations. Conditioning is required because the exit criterion for this stage — proven viability of the financing/insurance system at scale — is unmet and unevidenced. Releasing full scaling investment now would fund growth toward a ceiling the model has not shown it can pass.

# 5 · Scaling Strategy Review

## 5.1 Strategic diagnosis

JUDGEMENT  This is a strong innovation inside an incomplete scaling system. The team has done the hard technical and validation work exceptionally well and has secured two capable commercial partners. The strategy's gap is not effort or evidence — it is that the plan optimises the parts of the system that are already working (product, delivery, capacity) and under-specifies the part that isn't (the financing architecture that would carry the insurance leg to hundreds of thousands of farmers).

INTERPRETATION  Krupnik's meeting framing captures it precisely: this is the smallest track by adoption, taken on as a deliberate risk for its novelty and evidence, with an explicit ask to show a "systematic narrative of deep scaling" rather than just annual numbers. That narrative is the missing deliverable.

## 5.2 Priority actions

- Build the insurance-viability case — obtain from Dvara/ACRE and their insurers/reinsurer (Zep-Re) the minimum pool size for viable diversification and the acquisition-cost curve from 15k→500k. This is the gate-defining number.

- Write the subsidy-exit and financing plan — quantify subsidy/FLDG cost at 100k+ and name the committed source. Convert "crowd-in" from hope to a pipeline with probabilities.

- Instrument claims speed — measure days-to-payout against the planting calendar in 2026 as a first-class MELIA indicator.

- Open the agent black box — run the A/B / behavioural study with AoW5 on agent incentives and inclusion bias (the PhD study with U. Göttingen is the natural vehicle).

- Reconcile the facts — fix canonical reach/target/partner numbers (see §2.3) before external communication.

## 5.3 Owner-specific recommendations

| Owner | Recommended focus |
| --- | --- |
| IFPRI (Kramer) | Own the deep-scaling narrative and the insurance-viability evidence; convene the pool-math conversation with insurers/Zep-Re; lead fact reconciliation. |
| Alliance (Ramirez/Achicanoy) | Deliver climate-risk-pricing methodology under non-stationarity; make it the answer to Kohl's pricing question, not just model refinement. |
| Dvara / ACRE | Supply commercial terms + acquisition-cost data; state their own view of minimum viable scale and their subsidy-independence timeline. |
| S4I AoW4 (Investment) | Engage now on the crowd-in pipeline; the track's additionality depends on finance that AoW4 is positioned to help mobilise. |
| S4I AoW5 (Learning) | Co-design the agent-network and disadoption studies; treat this track as the portfolio's agent-network learning case. |
| Gender Accelerator | Move from equity monitoring to testing which delivery mechanisms actually protect inclusion at the agent interface. |

## 5.4 Adaptive management (decision rules, not fixed plans)

- If claims-to-payout consistently exceeds one planting cycle → escalate to a redesign of the payout trigger before expanding reach.

- If subsidy-funded uptake does not persist into the first unsubsidised season → pause reach expansion, diagnose willingness-to-pay before scaling further.

- If agent data show cream-skimming → adjust agent incentives before growing the agent network.

- If no committed subsidy financier emerges by Q4 2026 → re-scope ambition to the commercially self-sustaining denominator rather than 100,000.

## 5.5 Institutionalization assessment

JUDGEMENT  Institutionalization is commercial rather than public. The durable home of the innovation is the two enterprises' balance sheets, not a government scheme. That is legitimate and arguably more sustainable than a public pathway — provided the inclusive mandate survives commercialisation. The risk is a two-tier outcome: the product persists for creditworthy farmers while the women/youth/marginalised segment, which depends on subsidy and de-risking, is quietly dropped once S4I exits. Policy engagement was deliberately deferred; this caps the ceiling of the private-only pathway and should be revisited as a 2027 option, not closed.

## 5.6 Learning experiments

For each major uncertainty, the smallest experiment that would resolve it and the decision it would change:

| Uncertainty | Smallest experiment | Evidence produced | Decision changed |
| --- | --- | --- | --- |
| Insurance pool viability | Desk actuarial analysis with insurers/Zep-Re on min. diversification scale | Break-even farmer number | Whether 100k is even the right target |
| Subsidy exit | Track persistency of a subsidised cohort into first unsubsidised season | Renewal rate post-subsidy | Whether phase-out is feasible |
| Claims speed | Timestamp days-to-payout for 2026 claims | Payout latency distribution | Whether payout trigger needs redesign |
| Agent inclusion | A/B test agent incentive framing on who gets onboarded | Inclusion by farmer type | Agent incentive structure |
| Climate pricing | Backtest partner pricing vs. recent extreme events | Pricing error under non-stationarity | Whether reinsurance cover is adequate |

# 6 · Richard Kohl Coaching Preparation Brief

Note: Kohl already attended the 16 Jan 2026 meeting and put substantive points on the table. This brief anticipates his follow-up coaching, building on what he already raised (Syngenta precedent, pool viability, subsidy scale, climate pricing, the fine-print risk).

## 6.1 Executive coaching summary

JUDGEMENT  Kohl will almost certainly reframe the conversation away from "is the product good?" (he agrees it is) toward "what is the viable business model at scale, and who pays to get there?" The team should arrive having already done that reframing themselves — not defending the annual targets, but presenting the deep-scaling narrative Krupnik asked for.

## 6.2 Five questions Richard is most likely to ask

- What is the minimum farmer number for the insurance pool to be viable — and have your insurers and Zep-Re told you it in writing? (He cited Syngenta's 0.5–1m.)

- Who pays for customer acquisition and subsidies on the path from 15,000 to 500,000 — and is that money committed or hoped-for?

- How do your partners price risk when the historical time series no longer predicts climate and pest/disease events?

- How fast do claims actually pay out relative to the next planting and credit cycle — what's your evidence?

- What happens to the women/youth/marginalised farmers when the subsidies phase out — do they persist or drop?

## 6.3 Five assumptions he is most likely to challenge

- That credit-bundling solves the insurance-pool viability problem (it improves demand and adverse selection — it does not by itself create diversification).

- That "readiness 9" and RCT impact imply scaling readiness (his core technical-vs-scaling distinction).

- That crowd-in finance will materialise because the evidence is compelling (pending applications ≠ committed capital).

- That subsidies can be phased out on a fixed schedule regardless of whether persistency data supports it.

- That deferring policy/government engagement has no cost to the ultimate scaling ceiling.

## 6.4 Three areas where the team is likely overestimating readiness

- Financing pathway — treated as a communications/evidence problem ("make the case to investors") when it is a committed-capital problem.

- The 100,000 target — presented as a trajectory when it is an aspiration not reconciled with pool viability or the summed annual math (90,000).

- Inclusion delivery — targets are set (50/25/5) but the mechanism (agents) is admitted to be a black box; readiness of the inclusive wrapper is lower than the headline suggests.

## 6.5 Three strengths Richard is likely to recognize

- The bundling insight — attaching insurance to credit to defeat adverse selection and demand weakness is genuinely strong systems design.

- The evidence base — multi-site RCTs with real impact and welfare outcomes; unusually rigorous for a scaling track.

- Embedded MELIA + honest framing — the team names its own black boxes (agents, disadoption, trust) rather than hiding them, which Kohl values.

## 6.6 Evidence the team should have available

- Insurer/reinsurer statement on minimum viable pool size and current loss ratios

- Customer-acquisition cost curve and subsidy cost at 50k / 100k / 500k

- Committed vs. pipeline finance table (amounts, probabilities, dates)

- Claims-settlement latency data from existing operations

- Persistency/renewal rates from Dvara's existing 15k book

- The six RCT papers themselves (currently only cited)

## 6.7 Evidence currently missing

UNKNOWN  All of §6.6 except possibly the RCT papers is, on the supplied record, not yet in hand. The single most damaging gap in a Kohl session would be having no written answer on minimum viable pool size — because it is the question he has already flagged and will ask first.

## 6.8 Recommended 90-minute coaching agenda

| Time | Focus | Intended output |
| --- | --- | --- |
| 0–10 | Team reframes: present the deep-scaling narrative, not the annual targets | Shared problem framing |
| 10–35 | Insurance pool viability + subsidy financing (the weakest link) | Agreed minimum viable scale; funding-gap size |
| 35–55 | Climate-risk pricing under non-stationarity | Pricing/reinsurance strategy or explicit open question |
| 55–75 | Claims speed, persistency, and the agent black box | Prioritised 2026 learning experiments |
| 75–90 | Gate decision & sequencing (financing gate vs. agent focus) | Conditions for advancement; owners; dates |

## 6.9 Three conversations the team should have internally first

- With Dvara/ACRE and the insurers: "What is our honest minimum viable scale, and what does acquisition cost?" — before Kohl asks.

- With AoW4: "Is the crowd-in finance real, and what would make it committed?"

- Internally: "If no subsidy financier appears, what is our fallback ambition and are we willing to say 100,000 might be the wrong number?"

## 6.10 If Richard remembered only one thing six months later

The one thing "This team has the best product and evidence in the portfolio — and the least-defined answer to who pays to carry the insurance leg from fifteen thousand to half a million farmers. Fix the financing pathway and this is the strongest track; leave it and it repeats Syngenta."

# 7 · Operating System Improvement Recommendations

These concern the Scaling Intelligence Operating System itself, not the Solution Track. Kept deliberately separate per the brief.

## 7.1 By component

| OS component | Recommended improvement |
| --- | --- |
| Scaling Knowledge Standard | Require a mandatory "Reconciled Facts" card per track; flag any figure that appears with two values across documents. This track had 6 material inconsistencies that a standard field would have caught. |
| Scaling Intelligence Standard | Make the five-demand decomposition (user/market/payer/institutional/policy) and the additionality layer-test mandatory sections — both were decisive here and neither is a default template field. |
| Scaling Strategy Standard | Add an explicit "technical-readiness vs. scaling-readiness" divergence score, so a readiness-9 innovation cannot be read as scaling-ready by default. |
| Templates | Profile template should force a defined denominator (addressable population) and require annual targets to reconcile to the headline ambition. |
| Workflows | Route financing-viability questions to AoW4 automatically at intake; here the financing gap was visible from the EoI but AoW4 engagement was left to bilateral follow-up. |
| Weakest-link reasoning | Formalise the anti-legibility check as a required step — the tendency to name the fundable constraint (training) over the binding one (financing) recurred clearly here. |
| Stage-gating | Support component-level staging as standard: a track can be Scaling on one leg and PoC on another; a single overall gate hides this. |
| Coaching preparation | When a coach has already commented (as Kohl did), the prep brief should explicitly build on their prior comments rather than starting fresh. |
| Evidence handling | Distinguish "cited" from "supplied" in every evidence record; here the entire impact case rests on 6 unsupplied papers. |
| Repository structure | Add a cross-track heuristic library; "agent network as delivery black box" and "insurance pool viability" are portfolio-level patterns, not track-specific. |

## 7.2 Highest-value OS change

RECOMMENDATION  Adopt the technical-readiness vs. scaling-readiness divergence check as a standard gate input. This single addition would have surfaced this track's central issue automatically — a readiness/use score of 9 sitting next to an unevidenced scaling-system — and it generalises to the whole portfolio.

## 7.3 Assessor's provenance note

Every claim above traces to the supplied EoI, Profile, deck, minutes, or transcript, or is explicitly tagged INTERPRETATION / JUDGEMENT / UNKNOWN. No facts were introduced from outside the evidence base. The six cited academic papers were treated as asserted, not verified. This document is a working analysis; per repository governance it makes recommendations only and edits no repository object.