### Meeting Note: S4I Scaling Track Review - Shamba Shape Up / Munda Makeover

Date: January 29, 2026
Time: 1:07 PM
Attendees: Evan Girvetz (Chair), Pedro Chilambe (Presenter), Majambo Gamoyo, Richard Kohl, Marcel Gatto, Tim Krupnik, others from Alliance Bioversity-CIAT & CGIAR.

1. Presentation Summary: Scaling Edutainment for Agricultural Impact
Presenter Pedro Chilambe outlined the scaling track for the Shamba Shape Up (Kenya) and Munda Makeover (Zambia) edutainment platforms.

Objective: Scale a proven model for delivering agricultural advisory services via TV to 20 million households across East Africa by 2030, with an interim target of 16 million by 2028.

Current Reach: ~8 million viewers in Kenya, ~2.3 million in Zambia.

Evidence of Impact: Cited a University of Reading study showing 428,000 Kenyan households adopted new dairy practices, leading to a $24M net increase in production. In Zambia, 93% of viewers reported making farming changes.

Scaling Strategy:

Geographic Expansion: Consolidate in Kenya & Zambia, expand in Uganda, and introduce the model to Ethiopia.

New Pathway Test: Develop a Content Generation Platform to curate and repurpose scientific research into accessible content for broader dissemination.

Channel Diversification: Leverage iShamba/iMunda SMS services, social media (short reels, YouTube, Facebook), and explore radio and AI-powered tools.

2026 Focus: Consolidate learnings from 15+ seasons of KAP studies, produce content for other S4I scaling tracks, and establish the content platform.

Financial Model: In Kenya, ~60% of costs are covered by private sector partnerships (agribusinesses featuring solutions). In Zambia, funding is still primarily from development partners, with a goal to replicate Kenya's sustainable model.

2. Key Questions & Discussion Points

A. Financial Sustainability & Ownership (Post-S4I):

Q: Who pays long-term, and what is the sustainable cost-recovery model after S4I funding ends?

A: The goal is a blended model. Success in Kenya shows private sector agribusinesses will pay to feature solutions, covering a significant portion of production. The aim is to replicate this in newer markets like Zambia. Development partners may still fund specific thematic content.

Q: Who will own and maintain the content platform?

A: Not explicitly addressed. Requires clarification on long-term ownership (Mediae, CGIAR, government, hybrid).

B. Effectiveness, Inclusivity & Pathways to Impact:

Q: Is the focus on "reach" sufficient? How do we move to measured adoption of specific practices?

A: The team acknowledges the need to delve deeper. There is a large repository of longitudinal KAP data (15+ seasons) that needs analysis to understand adoption trends for specific innovations and identify barriers.

Q: The platform historically reaches better-off farmers. How is inclusivity addressed?

A: Efforts include gender-transformative content training, programs for youth, and diversifying delivery channels (SMS, roadshows, radio) to reach those without TVs. Roadshows also included input marketplaces to improve access.

Q: How does this compare to other extension channels (digital Green, AI chatbots, public extension)?

A: Internal KAP surveys consistently show farmers prefer and find TV/video demonstrations more useful than radio or text. A formal comparative analysis with other digital channels was suggested as a valuable addition.

C. Learning, Evaluation & S4I Additionality:

Q: How can AoW5 support rapid evaluation and adaptive learning (e.g., A/B testing, quasi-experimental designs)?

A: There is a major opportunity for a longitudinal analysis of existing KAP data to generate intelligence on what works. The real-time nature of SMS feedback (iShamba) also offers potential for rapid testing cycles. Collaboration with AoW5 was encouraged.

Q: Can we "learn from failure" and test channel combinations for complex innovations?

A: This aligns with the proposed deeper dive into KAP data and the experimentation with new channels (social media, AI). Structured learning agendas are needed.

Q: What is the clear S4I additionality? What wouldn't happen without it?

A: S4I enables testing a new scaling pathway (the Content Generation Platform), systematic cross-country learning, strengthening scientific rigor in content, and potentially faster transition to financial sustainability in new regions.

Q: What does success look like in 2026 and 2028?

A:

2026: Successful launch and initial use of the content generation platform. Consolidated learning from past data.

2028: Platform actively feeding multiple dissemination channels (TV, social, AI tools). Viewer base reaches 16 million. Clear evidence of a sustainable, multi-channel model emerging.

D. Operational & Strategic Points:

Influencers: Brief discussion on using social media influencers or celebrity ambassadors (e.g., athletes) to amplify reach. This remains an area for exploration.

Process for Innovations: A request was made to define a clear process for how other CGIAR innovations or partners can engage to have their solutions featured on the platform.

3. Action Items & Next Steps

For Presenting Team:

Share presentation deck with S4I management for distribution.

Refine answers to core questions on sustainability, ownership, and S4I-specific outcomes.

Explore collaboration with Area of Work 5 on a dynamic learning agenda and evaluation design.

For S4I Program:

Synthesize materials into a draft Scaling Track Profile for review.

Schedule follow-up in April 2026 to review progress, particularly on evaluation plans and platform development.

Identify specific support needs from S4I (e.g., scaling strategy, enabling environment analysis for new countries).