Scaling Track: Solar-Powered Irrigation Systems (SPIS) – IWMI

Countries: Nigeria, Ethiopia, Kenya

Current Situation: Technical feasibility is well established: High ROI across crops, positive BCR in Ethiopia, IPSR profiling completed, South–South experience (India, Bangladesh). Technology readiness is not the binding constraint.

Key Limiting Factor: The primary constraint is system-level financial and institutional integration, not technical validation. SPIS remains project-financed or vendor-driven, dependent on pilots and development programs, weakly embedded in formal agricultural finance systems, and not yet institutionalized in irrigation governance structures.

The scaling question to answer: What institutional or financial rule/process must change within 24 months to mainstream SPIS into national agricultural finance systems?

Existing bilaterals: (SoLAR II, NSSID, ACReSAL, Irrigation Investment Tool) already cover demonstrations, evidence generation, capacity building, stakeholder engagement, initial policy dialogue, and vendor partnerships. If S4I focuses on awareness, training, or additional pilots, duplication risk is high.

S4I Additionality: Proposed S4I activities emphasize training, demonstrations, evidence consolidation and capacity building. These risk duplication or at least doing more of the same thing, and do not represent system-level leverage.

To maximize additionality, this scaling track should consider focusing on:

- Embedding SPIS into Formal Agricultural Finance: Standardized SPIS credit products, guarantee mechanisms, central bank/agricultural bank risk modeling, integration into subsidy or credit frameworks

- Structuring Blended Finance Vehicles

- Defining Exit Criteria and clear institutional milestones for withdrawal: e.g. Adoption of national SPIS finance guidelines; Launch of blended finance facility; IFI-backed investment secured; Policy integration formalized

Overall summary: High technical readiness, moderate market readiness, low institutional embedment clarity. Requires sharper system-level positioning to justify S4I engagement.

Core Strategic Questions to discuss in next 1-on-1 meeting:

- What is the binding constraint -- finance structuring, irrigation governance reform, or private-sector market depth? Which binding constraint can realistically be addressed in 24 months?

- Does the current S4I budget allocation support system reform — or primarily project activity? What defines successful “exit” from S4I support?

- How long are you going to continue long term sustainability without donor support after 2028?

Notes from 13 Feb 2026 AoW2 meeting

Richard:

These things are really expensive and take time for a smallholder farmer

Mostly for more well off famers

Difficult to install by our selves

Small country subsidy programs to dig water pits

Criticism in the past is that

Imported—tariffs high (?) expensive

Even if a short term blended finance pathway, what happens after