Market led partnerships for resilient agri-food systems in Terai region of Nepal

Scaling for Impact Science Program

Area of Work 2

Flagship Solution Scaling Tracks
Inception Meeting and Process

Dyutiman Choudhary - CIMMYT

Narayan Khanal- CIMMYT

Santosh Nepal – IWMI

Sanju Koirala - IWMI

Version: 1.0

Submitted to: Tim Krupnik, Director, Scaling for Impact Science Program, CGIAR

Date: 09 January 2026

Work plan details

- Innovation package

What are the innovations you are planning to bundle and scale?

A tested market-system approach with public-private-cooperatives partnerships to deliver i) quality seed (hybrids, OPVs, local landraces), ii) soil fertility (extension, advisories on 4Rs, N fixing and green manuring crops, nutrient enriched composts; machinery with soil amendments) and iii) irrigation inputs (on-farm water management; water distribution) to small holder farmers; and iv) multi stakeholder platforms with public private partners.

Provide evidence on the profitability or cost-effectiveness of the innovation(s) for end users (why they are motivated to adopt)

Since 2022, these technology bundles coupled with supportive policies and markets have led to a 20-40% increase in the yield of rice, legumes, vegetables and about 100% for maize, leading to improved food security, household incomes and input business growth.

The introduction of seed drills cut sowing costs from US $53 to $26 per hectare, and machine planting was used by 29% of farmers. About 70% of farmers were using hybrid seeds and 87% practicing line planting for better efficiency. Best management practices, such as targeted urea application and block production, led to a 15% reduction in production costs and improved climate resilience.

From 2021 to 2025, spring maize adoption in western Terai soared by 700%, covering 2,000 hectares. Annual maize sales value of partner cooperatives reached US $3.3 million, which is an 850% increase since 2021. Average farm gate prices increased by 81% from Rs 21 in 2021 to Rs 38 in 2025. Table 1 shows the perception of stakeholders from Western Nepal from the target areas on innovation use in 2025. These innovations could be expanded into new areas in partnership with public and private sector stakeholders in a gender-balanced, inclusive and environmental sustainability manner.

How are these innovations assembled into a bundle and how do you anticipate packaging them?

- Develop an outline of the cropping calendar by province; prepare crop specific operations outline for each production area

- Organize innovation platform meetings for demand and supply assessment (potential area (location & ha), coops, quantity of inputs, suppliers, buyers) focused on the identified technologies on seed, soil fertility and irrigation.

- Develop package of practices of technology bundles for dissemination to farmers and stakeholders

- Promote improved irrigation facilities and on-farm management practices for targeted crops, including efficient water application methods and scheduling aligned with crop growth stages and context specific irrigation technologies.

- Facilitate market actors to develop input roadmaps and investment plans and will be trained to provide extension services, as part of their product sales and promotions, to farmers at various cropping stages.

- Develop linkage with local and provincial governments for crop production programs and extension.

- Develop cooperative level production plans with various category of farmers and inclusive technology delivery strategies

- Organize training programs for lead farmers, follow up training for beneficiary farmers, training for local colleges and institutions, virtual calls and provide digital advisories on technology bundles through public and private sector channels

- Monitor production and technology use through local governments, local universities, market actors and cooperatives and through virtual calls

A blog for bundling Innovation.docx

What evidence do you have or will collect that the innovations can be scaled responsibly? (insights on potential negative impacts for specific groups, and mitigation)

CIMMYT and IWMI conducted a scaling assessment with stakeholders using the scaling scan tool (www.scalingscan.org)  to assess the scalability of the maize commercial model (MCM), a production to market system innovation, initiated by CIMMYT and its partners. During the session stakeholders prioritized potential socio-technical innovation bundles for maize and other crops in the cropping system that could best scale the production of these crops.

https://www.cgiar.org/news-events/news/scaling-maize-production-in-nepal-the-mcm-initiative

Social and environmental responsibility checks show that the scaling process is socially equitable where men, women and youth from various caste and ethnicities collaborate and environmentally sustainable with the promotion of climate resilient practices. The pathways include women, youth, Dalit, Muslim and indigenous people leading to their profitable integration in crop value chains.

IWMI has recently developed an integrated monitoring of irrigation systems (flow, meteorological and soil moisture sensors) in Babai irrigation system. The dashboard is now formally hosted in the National Irrigation and Infrastructure monitoring system (NIIMS), supporting informed water allocation and planning at the field level. We will leverage this system in Babai irrigation command area to support spring maize production.

Indicate the outcome target (2026, and longer-term) for the solution track - Any changes since the proposal submission?

Longer term

- About 237,500 HHs with 1.2 M persons (40% are women and youth), will be reached to produce rice, maize, legumes, and vegetables, in about 257,730 ha across 11 districts of Koshi, Lumbini and Sudurpaschim provinces.

- The intervention will benefit 800,000 consumers with quality food and will add value to 10,000 jobs in the ag inputs sector.

- The interventions will result in enhanced irrigation facilities across 10,000 ha of maize-paddy-vegetable producing land in Lumbini and Sudurpaschim province, significantly boosting crop diversification and productivity.

- The pathway will unlock new business opportunities with public private and donor funding of about USD 30 million.

2026 outcome

- HH – 39,300 (rice) + 19000 maize

- Number of individuals – 49,000

- Expansion of irrigated area for spring /winter: 2000 ha

- Estimated area covered by improved seed, fertilizer and irrigation (ha)- 50,000

- Consumers benefited – 200,000

- Consumers for value added foods – 100,000

- Jobs: 3000 (eastern market – 70%) and western – 30%

- Investments leveraged – USD 10M

What behavior change and system improvements are being targeted with the S4I investment that would result in enhanced scaling?

- S4I investment is fostering cropping system improvement by promoting a profitable maize crop in rice fallows for crop diversification and income generation by promoting technology bindles and innovative business processes.

- A steep uptake of the cropping system diversification approach is contributing towards self-sufficiency of maize in Nepal leading to increased demand for scaling– “Scaling Out”

- S4I investment is fostering a market system development approach with multi stakeholder engagement to scale crop production by promoting technical and business process innovations – “Scaling Deep”

- S4I investment is fostering improved input and output market development leading to more efficient and profitable market systems in Nepal.

- S4I investment is targeting the change in the Government of Nepal’s (GoN) program scaling strategies with public private partnerships - “Scaling Up”

- S4I investment is fostering new investments from Nepal’s Ministry of Agriculture and Livestock Development (MoALD) for scaling innovations from Western to Eastern Nepal

What scaling challenges does the S4I investment allow you to mitigate or test?

- The S4I investment allows us to bring public private and community stakeholders into a common platform for fostering technology uptake and design scaling strategies in a predominantly unorganized market system.

- The S4I investments allows us to generate investments from public, private, and farmers cooperatives for scaling technology uptake and innovations focusing on a common vision which is rarely seen in Ag market systems in Nepal.

- The S4I investment allows us to design and test pathways that scale innovations in a responsible manner for Ag sector program design and investments. Such investments allow knowledge and evidence-based scaling strategies by market actors that are not available to them for effective decision making

- The S4I investment allows us to design and test inclusive strategies to scale CGIAR technologies through innovation bundles.

Demand Partners

Partners who motivate for this solution track (differentiate by type, sector, etc)

Farmers Institutions

Grain producer cooperatives: The track will facilitate farmer cooperatives to develop strategic plans for a) organizing and managing demand of agri-inputs and provide technical services for their members, b) facilitate output aggregation and contracts with buyers, and c) participate in multistakeholder platforms to co-design pathways that facilitate scaling agri-inputs technology bundles.

Private sector

Agro dealers: These include businesses selling seed, fertilizers, agriculture machinery, and irrigation equipment.  As part of their marketing strategies, they will provide agro-advisory services and other embedded services to farmers. These actors will receive training to promote and sell their products and services.

Seed companies & cooperatives: These actors will receive mentorship support on market intelligence and understanding demand from buyers through multi-stakeholder platforms. They will be strategically linked with the grain producer cooperatives for providing quality seeds of the demanded varieties on time through appropriate channels.

Feed/food mills/MSMEs: These actors mainly represent the output markets and will participate in multi-stakeholder platforms and place the demand of commodities including volume, pricing, quality of products and purchase mechanisms. Assured markets will motivate the grain producers to use CGIAR technology bundles to produce outputs as per market demand.

Identify the CG Science Program that is linked with the innovation

Breeding for Tomorrow

What evidence do you have that the S4I intervention is demanded by partners?

During 2025, we organized 3 workshops on scaling CGIAR innovations in Western and Eastern Nepal including field visits. We consulted stakeholders including farmers, input suppliers, industries, and business associations about the status, issues, emerging changes, opportunities and potential pathways to transform the agrifood system in an inclusive and sustainable way. We found that input market actors are poorly connected with farmers and output markets. As a result, there is less investment from the private sector in stocking and expanding markets. Most farmers are unaware of modern farm inputs and sometimes do not receive them on time. Input market actors and farmers are keen on using CGIAR innovations on seed, soil fertility management, machinery, and irrigation to boost crop production and input sales.

Stakeholders in a scaling scan workshop in Bardiya in May 2025 prioritized seed, ISFM and irrigation as the most important inputs to expand maize commercialization (figure below)

What evidence do you have that the scaling pathway you have chosen is demanded and supported by each partner?

In 2025, CIMMYT together with CCDABC organized multi-stakeholder workshops where stakeholders clearly reflected the need for promoting agri-input markets for the transformation of agri-food system and showed their commitments to participate in the promotional programs:

Report 1: Workshop Report_Eastern_Terai.docx

Report 2: Visit and Workshop Report_Khajura_Banke_Nov 2025 (1).docx

How do you engage with demand partners to support scaling?

The demand partners will be engaged in the process of agri-input sector assessment, training, MSP meetings, co-design of technology delivery pathway meetings, review and planning meetings etc. Demand partner-wise engagement activities have been explained in the annual activity plan.

Scaling Partners

Partners who will support the scaling process

Local government: These actors will participate in local level multi-stakeholder platforms and share and update their existing programs as per the need for stakeholders. They will facilitate developing strategic linkage with other actors (e.g. provision of electricity for irrigation) and increase/update budget for agri-inputs which can amplify the scaling process

Province government: They will participate in the district-level MSPs, joint monitoring visits, co-design workshops with stakeholders, contribute to developing agri-input road maps, revise/allocate budget to fund and expand scaling of agri-inputs.

Irrigation offices of Babai and Rani-Jamara-Kulariya: These two large irrigation systems will support by providing dedicated water to selected fields for spring maize cultivation.

Federal government: They will participate in the agri-input assessment and road map preparation process, revise/update/increase investment in agri-inputs by linking with the on-going projects such as MCM, Rice mill model, rice seed production project under JICA

Business associations:

Seed Entrepreneurs' Association of Nepal (SEAN): Participate in network meeting & co-design workshop, agri-input fairs, investment meetings, policy dialogues, and facilitate their members to increase investment for the production and distribution of farmers demanded seeds in different market segments. They will also collaborate with business associations of India and Bangladesh to introduce and promote farmers’ demanded varieties

Nepal Agriculture Machinery Association (NAMEA): Participate in network meeting & co-design workshop, agri-input fairs, investment meetings, policy dialogues, and facilitate their members to increase investment for the production and distribution of farmers demanded machines in different market segments. They will also collaborate with business associations of India and Bangladesh to introduce and promote farmers demanded agricultural machineries.

Confederation of Nepalese Industry (CNI): The track will collaborate with CNI to develop a vision document to increase investment in agriculture sector in Nepal in next 10 years focusing on agri-inputs such as seed, soil fertility management and irrigation. The CNI will participate in GoN high level meeting to influence the policy change in favor of agri-input market development

Feed Mills: Feed and food mills will participate in agri-input assessment process, network meetings, and co-design of technical bulletins. They could also make buyback agreements with the grain producers during the network meeting and provide input bundles (seed, fertilizer, credit, irrigation) to farmer groups/cooperatives to ensure the quality of grain demanded.

NGOs and development partners- These actors will participate in network meetings and co-design workshops to update/develop plans to support agri-input market system from their on-going project activities.

How do you know these partners are the best ones to work with on this innovation scaling process (please be self-critical)?

We organized strategic meetings, reviewed on-going project profiles, and activity and budget documents of the above partners for 2025/2026. The insights below from the assessments show that these partners are most relevant to work with the scaling track:

- Government of Nepal in 2025/26 programs and budget has emphasized the promotion of agri-inputs including seed, organic manures, irrigation and mechanization and expected collaboration from partner organizations

- https://doanepal.gov.np/downloadfile/Red%20Book%202082_1749469664.pdf

- The Ministry of Industry, Agriculture and Cooperatives, in Koshi province, has allocated budgets for providing subsidized loans to agri entrepreneurs for market development and use of agri-inputs. The province has prioritized improved seed, soil fertility management, and mechanization.

- https://moeap.koshi.gov.np/content/63/a-w-the-budget-statement-of-2081-082/

- The Ministry of Land Management, Agriculture and Cooperative (MoLMAC), Sudurpaschim province has prioritized seed production, soil health card distribution, soil organic matter improvement through legume promotion, area expansion of maize and fine & aromatic rice varieties. The track could provide technical and strategic inputs to these on-going programs to enhance their efficiency, inclusivity, targeting and sustainability

- https://moea.sudurpashchim.gov.np/content/12570/program-booklet-2082-83-fiscal-year-2082/

- The Ministry of Agriculture and Land Management (MoALM), Lumbini province prioritized seed, fertilizer, mechanization and irrigation in the current (2025/26) program and budget. The project could provide technical and strategic guidance to enhance the efficiency of these programs, increase investment in the sector, and reach out to the needy households

- https://moeap.lumbini.gov.np/en/notice/218

Will partners be funded? How will they be motivated?

Partners will not be funded by S4I. They will be motivated to receive validated technologies and delivery pathways that will add value to their existing programs or to design new projects. CIMMYT has already supported the MoALD to design and fund a new program on commercial maize production which will be continued in 2026.

Clearly describe the scaling pathway:

  - Where is the technology bundle being scaled?

The technology bundles and process innovation will be scaled in 3 provinces of Nepal covering 7 districts.

  - How will it reach the last mile in a sustained way?

- Prepare an outline of the cropping calendar by province; make crop specific operations outline for each production areas

- Organize innovation platform meetings for demand and supply assessment (potential area (location & Ha), coops, qty of inputs, suppliers, buyers) focused on the identified technologies on seed, soil fertility and irrigation.

- Develop package of practices with technology bundles for dissemination to farmers and stakeholders

- Develop linkages with local and provincial governments for crop production programs and extension.

- Develop cooperative level production plans with various category of famers and inclusive technology delivery strategies

- Organize training programs, virtual calls and provide digital advisories for extension workers, lead farmers and facilitate follow up trainings

- Monitor production and technology use through local governments, local colleges, market actors and cooperatives and virtual calls

- Local Ag colleges will be mobilized for providing technical training to lead farmers, market and extension agents and to monitor the use and application of inputs and their impacts on improved crop production for feedback to local and provincial Governments.

- Who is paying for it and supporting it?

- The Local and Provincial Governments will invest in smart subsidies on seed, soil fertility, mechanization and irrigation technologies, training and formation of innovation platforms. Their extension workers will train farmers and market actors.

- Irrigation projects will support irrigation water availability to scale production

- Private sector businesses will invest in demanded seed, soil fertility management, mechanization and irrigation technologies and deliver to farmers

- Farmers’ cooperatives will aggregate demand and provide bulk purchasing services for the required inputs for member farmers.

- Farmers will pay for all input used for crop production, unless made available under Government subsidy

- Farmers cooperatives will also provide credit to their member farmers

- Insurance companies will make group insurance schemes

- Banks will support working capital loans through the contract between buyers and sellers

- Millers and processors will design contractual arrangements with cooperatives to supply inputs and purchase commodities.

- What evidence do you have that this is the best scaling pathway to pursue, as opposed to alternative pathways (please list alternatives)

The scaling pathway proposed in this track includes a public private and community partnership approach. Technology bundles are supported by improved market mechanisms, supportive policies and market governance mechanisms to support upgrading of crop market system. The approach has been tested and improved since 2022. The pathway has shown considerable progress in terms of spring maize growing farmers households increasing by 700% in the pilot phase.

Alternatives:

- Donor money used to purchase inputs for distribution by Government agencies which is highly unsustainable due to lack of a demand pool and market distortion.

- Local Governments disseminating technologies to farmers to boost production often lack private sector participation and often lose pace in providing support as needed by farmers and market actors.

- Private sectors alone may find it expensive and outside their business practice in an evolving market to gather tested technologies for dissemination among farmers and buy-back, without the support of local governments and farmers cooperatives.

- Can you pivot to new pathways if needed?

New pathways can be pivoted if significant new market opportunities such as ethanol, silage etc emerge for maize.

- Highlight catalytic leverage: partners, geographies, policies, agribusinesses, bilateral projects

Partners: 14 seed producer cooperatives, 35 farmer cooperatives, 28 agrodealers, 28 MSMEs & 21 local governments, Ministry of Agriculture and Livestock Development (MoALD); Department of Water Resources and Irrigation (DWRI), irrigation projects, 4 Water User Association Groups of Babai and Rani-Jamara-Kulariya irrigation systems.

Geography: Huge spring fallow areas in the Terai suitable for maize; emerging business and private sector investments is catalyzing demand.

Policies: ADS has prioritized crop value chains as a flagship. Provincial and Local Governments have a priority for improved crop production and rural livelihoods.

Agribusiness: 7 seed companies, Feed mills and food processing industries, Nepal Seed Entrepreneur Association (SEAN), Nepal Agriculture Machinery Association (NAMEA), Confederation of Nepalese Industries (CNI).

Bilateral Projects: Several Government and donor projects being implemented for agriculture development will scale CGIAR technologies

- 6 Agriculture Knowledge Centers and 1 Integrated Agriculture and Livestock Development Office (IALDO) in 7 districts and 3 provinces (Lumbini, Sudurpaschim and Koshi) to harmonize provincial activity plans (e.g. pocket and block production program, output-based incentive, chief minister agriculture modernization program, agriculture financing programs, marginalized community and youth focused programs) in line with market-based approach for seed and ISFM scaling.

- Engagement with local Government Ag sector plans – local Government allocated USD 3.5 M in 2025 to support seed, irrigation and crop production in 50 municipalities in maize commercial model sites.

- Partnership with MoALD’s rice mill model- This program is being implemented in 20 Terai districts (50 municipalities) and about 100 rice mills associated with 20,000 farmers are engaged in this program. There is potential for seed producers and input suppliers to sell 1,500 Mt of climate resilient, short duration and fine quality rice seed and apply ISFM technologies for rice production. After distributing seed, the millers sign buyback agreements with farmers to ensure output market linkage.

- Partnership with MoALD seed and soil fertility programs through the Centre for Crop Development and Agrobiodiversity Conservation (CCDABC) that allocated USD 200,000 to 25 municipalities in FY 2025/26 for promotion and scaling climate resilient seed of multiple crops, fertilizer and irrigation innovations within and beyond the S4I track sites

- Agriculture and Forestry University in Koshi province and Far Western university in western Terai are actively engaged in mobilizing intern students for technology demonstration, awareness raising and implementing “learning and earning” programs which could be linked to this initiative.

- Partnership with the MoALD-JICA partnership “seed production and marketing” project being implemented in Eastern Terai districts (Jhapa, Morang and Sunsari) for promoting seed and ISFM technologies.

Present the specific activities that will be funded by S4I?

Activities will focus on three components viz., i) farmer and stakeholder mobilization, ii) input market development and iii) delivery and knowledge assisted public private-cooperative partnerships.

Specific theme activities are provided below:

Farmer and stakeholder mobilization

- Develop and strengthen multi stakeholder platforms for input market system coordination; develop input delivery and distribution strategies with public and private actors.

- Prepare road maps for seed (OPV, hybrids, local land race production/import, distribution and delivery)

- Develop a strategy to apply balanced soil fertility management technologies the 4Rs (right source, right rate, right time, right place) of nutrient management,

- Prepare a water supply, irrigation equipment, and machinery delivery strategy for efficient use and delivery at key crop stages.

- Support to develop an irrigation scheduling and plot-based water management strategy

- Develop agroclimatic zone wise cropping calendars.

- Conduct farmer mobilization and orientation programs at the various sites in the 3 provinces

- Develop a strategy for promoting digital platforms for extension and advisor

- Conduct training on technology bundles with extension agents and lead farmers.

Input market development and delivery

- Support the delivery of seed, ISFM, machinery and irrigation inputs product to farmers;

- Develop and implement last mile distribution systems with public private partnerships;

- Conduct training for market actors and extension workers on input delivery and extension;

- Support seed and machinery associations with new research and business insights for investments.

- Link market actors with farmer cooperatives and large Ag development programs for supplying quality inputs throughout the cropping season.

- Strengthen output market linkages to create a self-sustaining business model for ag inputs and outputs.

Delivery and knowledge assisted public private-cooperative partnerships

- Developing joint ag input market development strategy with the public and private sector and industry associations.

- Develop partnerships with donor and Government of Nepal programs for generating investments; Conduct market assessments

- Conduct annual monitoring of activities with local knowledge partners such as universities and colleges.

- Support to organize local trade fairs, investment forums, policy dialogues to boost the delivery of quality ag inputs to farmers.

What specific bilateral projects (of CG Centers or partners) will these activities build on?

This track will mainly support and strengthen scaling and demand partners programs as highlighted below:

- Pocket and block production program, output-based incentive, chief minister agriculture modernization program, agriculture financing programs, marginalized community and youth focused programs of the provincial Governments – USD 3M

- MoALD’s rice mill model- This program is being implemented in 20 Terai districts (50 municipalities) and about 100 rice mills associated with 20,000 farmers are engaged in this program. There is potential for seed producers and input suppliers to sell 1,500 Mt of climate resilient, short duration and fine quality rice seed and apply ISFM technologies for rice production. After distributing seed, the millers sign buyback agreements with farmers to ensure output market linkage. USD 1M by government, USD 2M by private

- Partnership with MoALD seed and soil fertility programs through the Centre for Crop Development and Agrobiodiversity Conservation (CCDABC) that allocated USD 200,000 to 25 municipalities in FY 2025/26 for promotion and scaling climate resilient seed of multiple crops, fertilizer and irrigation innovations within and beyond the S4I track sites

- Partnership with the MoALD-JICA partnership “seed production and marketing” project being implemented in Eastern Terai districts (Jhapa, Morang and Sunsari) for promoting seed and ISFM technologies. USD 1.5M

- Agriculture and Forestry University in Koshi province and Far Western university in western Terai are actively engaged in mobilizing intern students for technology demonstration, awareness raising and implementing “learning and earning” programs which could be linked to this initiative.

- The CGIAR Policy Innovations Program will evaluate lift irrigation prospects in western Nepal, potentially facilitating the expansion of market-driven approaches for key crops such as spring maize in the mid-hill regions.

Province specific programs

Koshi province

- Strengthening rice seed production centers/groups/cooperatives- USD 0.1M

- Promote organic fertilizer- USD 0.2M

- Subsidized loan (5% interest subsidy to agri-enterprenurs); USD 3.2M

- Action research through local college- USD 0.2M

Lumbini province

- Support on irrigation infrastructure- USD 0.5M (additional irrigation in 1300ha)

- Crop production expansion: rapeseed-500ha, rice 300ha, lentil 100ha, maize & soybean-240ha

- Support to specialized group (dalit, muslim, women) in agriculture: USD 0.2M

Sudurpaschim province

- Learning and earning program- USD 0.5M

- Seed production and distribution - USD 50,000

- Agri-ambulance for transportation services - USD 0.8M

- Promotion of green manure and organic fertilizer- USD 40,000

- Soil health card promotion- USD 2000

- Vermi-compost production- USD 2000

What are these projects’ dates and budget that can be leveraged? Are these already mapped to S4I through CGIAR’s PRMS?

Budgets are mentioned against the projects above. These are yet to be mapped to PRMS.

Provide a timeline for the scaling track

A three-year high-level cross-center work plan

- Shared in an excel file

A one-year more detailed cross-center Gantt chart for 2026 activities

- Shared in an excel file

Highlight key moments in the timeline for outputs and outcomes to be produced and linked to communications

  - In your estimation, when can communications support be provided to document and share the outcomes?

At the service delivery and production stages as per the cropping calendar for each crop in 2026.

Theory of scaling and change

Describe at a high level what your theory of change to lead to impact at scale?

The solution tracks theory of change is premised on moving poor and semi subsistence-oriented smallholder farmers towards more modern and commercial farming for sustainable incomes and household-level food and nutrition security across the three provinces covering seven districts.

Despite the availability of and large potential for improved seeds, integrated soil fertility management (ISFM) and irrigation technologies to boost productivity, less efforts have been made to develop their markets in Nepal. The agriculture sector is constrained by a lack of knowledge and spatially explicit technologies and practices related to crop seeds, soil fertility and irrigation management, and the lack of a farmer-responsive market system for these critical inputs. CIMMYTs and IWMI evidence show that improving private sector services, generating public-private and community partnerships and responsible and inclusive value chain mechanisms, has the potential to create sustainable demand for agricultural technologies in Nepal.

This track will focus on promoting markets for identified technology bundles and support the scaling of these technologies through improved partnerships, business practices and extension approaches. The track will prioritize three components, viz., i) farmer and stakeholder mobilization; ii) input market development and delivery and iii) knowledge assisted public private-cooperative partnerships. Public and private sector actors will be supported to promote CGIAR tested technologies on improved seed, ISFM, scale appropriate mechanization and irrigation, alongside innovations for input and output market governance and multi-stakeholder platforms through CIMMYTs maize commercial model (MCM) that has been in operation since 2022. The use of these technologies will increase production, which will help household food and feed security while surpluses can be sold to generate additional income. The increased production will support local agribusinesses and micro small and medium enterprises (MSMEs) to develop supply chains from locally sourced commodities which will be inclusive, sustainable and resilient. Increased incomes should incentivize investment in CGIAR technology bundles and other asset-building activities by farmers and market actors, resulting in more demand for quality inputs. As project interventions are designed for different types and classes of farmers, the transformation will be inclusive and will cater to the needs of smallholder farmers in Nepal’s rural and disadvantaged areas.

The track will produce evidence to generate investments from public and private sectors to the scale the supply and use of technological innovations in agriculture-related businesses. Track interventions are designed to bring about sustained changes in market systems in the following ways:

Technology bundles will introduce improved seed varieties, ISFM, mechanization and water management interventions supported by training, market linkages, digital platforms and supportive policies and value chain coordination mechanisms.

Market interventions focus on innovative ways of doing business, improved access to services and finances for crop production, diversifying product choices for farmers, and engagement with development partners for scaling up and out through tested scaling pathways.

Policy and market development interventions will open the scope for business expansion and provision of technologies by the public and private sectors. An enabling environment consisting of a supportive policy, legal and regulatory environment at the local level will be fostered for the sustainable growth of market-based input business.

As envisaged by the Agriculture Development Strategy (2015–2035), the track promotes responsible, inclusive, efficient and remunerative value chains. This should contribute to boosting the competitiveness of the agri input and output sector, thereby increasing investments in agriculture. This should, in turn, contribute to the inclusive and sustainable growth of the agriculture sector and enhance food and nutritional security.

What is your theory of action (what you will do) along the chosen scaling pathways to (catalytically) contribute to the high-level theory of change?

Activities will focus on three components viz., i) farmer and stakeholder mobilization, ii) input market development and iii) delivery and knowledge assisted public private-cooperative partnerships.

Specific component wise activities are provided below:

Farmer and stakeholder mobilization

- Develop and strengthen multi stakeholder platforms for input market system coordination; develop input delivery and distribution strategies with public and private actors.

- Prepare road maps for seed (OPV, hybrids, local land race production/import, distribution and delivery)

- Develop a strategy to apply balanced soil fertility management technologies the 4Rs (right source, right rate, right time, right place) of nutrient management,

- Prepare a water supply, irrigation equipment, and machinery delivery strategy for efficient use and delivery at key crop stages.

- Support to develop an irrigation scheduling and plot-based water management strategy

- Develop agroclimatic zone wise cropping calendars.

- Conduct farmer mobilization and orientation programs at the various sites in the 3 provinces

- Develop a strategy for promoting digital platforms for extension and advisor

- Conduct training on technology bundles with extension agents and lead farmers.

Input market development and delivery

- Support the delivery of seed, ISFM, machinery and irrigation inputs product to farmers;

- Develop and implement last mile distribution systems with public private partnerships;

- Conduct training for market actors and extension workers on input delivery and extension;

- Support seed and machinery associations with new research and business insights for investments.

- Link market actors with farmer cooperatives and large Ag development programs for supplying quality inputs throughout the cropping season.

- Strengthen farmer- output market linkages to create a self-sustaining business model for ag inputs and outputs.

Delivery and knowledge assisted public private-cooperative partnerships

- Develop joint ag input market development strategy with the public and private sector and industry associations.

- Develop partnerships with donor and Government of Nepal programs for generating investments

- Conduct market assessments

- Conduct annual monitoring of activities with local knowledge partners such as universities and colleges.

- Support organizing local trade fairs, investment forums, and policy dialogues to boost the delivery of quality ag inputs to farmers.

How do you know or what evidence do you have that the chosen pathways are the best ones and that the S4I actions are the key bottlenecks to be addressed?

- Scaling MCM- Nepal Public Policy Review.pdf

- NSAF Closeout report_210325.pdf

- Nepal uses digital soil map for the first time in SAARC

- धान, मकै र गहुँमा हाल्ने मलको मात्रा तोकियो, कहाँ कति हाल्नुपर्छ?  :: सुनिता सिटौला :: Setopati

- From seed to feed – CIMMYT

- Nepal Government endorses new site-specific fertilizer recommendations for rice – CIMMYT

- Balanced fertilizer application boosts smallholder incomes – CIMMYT

- Driving innovation through digital agriculture: Digital Ag Nepal, 2024 – CIMMYT

What criteria have you considered / what evidence do you have that the chosen pathways are best for this innovation scaling process?

The following evidence suggests that the chosen pathways are best for the innovation scaling process:

From 2021 to 2025, spring maize adoption in western Terai soared by 700%, covering 2,000 hectares. Annual maize sales value of partner cooperatives reached US $3.3 million, which is an 850% increase since 2021. Average farm gate prices increased by 81% from Rs 21 in 2021 to Rs 38 in 2025. Table 1 shows the perception of stakeholders from Western Nepal from the target areas on innovation use in 2025. These innovations could be expanded into new areas in partnership with public and private sector stakeholders in a gender-friendly, inclusive, and environmental sustainability manner.

CIMMYT and IWMI conducted a scaling assessment with stakeholders using the scaling scan tool (www.scalingscan.org)  to assess the scalability of the maize commercial model (MCM), the production to market system innovation initiated by CIMMYT and its partners. During the session stakeholders prioritized potential socio-technical innovation bundles including agri-inputs from maize and other crops in the cropping system that could best scale the production of these crops.

https://www.cgiar.org/news-events/news/scaling-maize-production-in-nepal-the-mcm-initiative

Social and environmental responsibility checks show that the scaling process is socially equitable where men, women and youth from various caste and ethnicities collaborate and environmentally sustainable with the promotion of climate resilient practices. The pathways include women, youth, Dalit, Muslim and indigenous people leading to their profitable integration in crop value chains.

​Scaling the MCM.docx​

S4I additionality

How are S4I resources (funds, expertise, etc.) supporting the on-going scaling process from the bilateral project

- A steep uptake of the cropping system diversification approach in the Terai is contributing towards self-sufficiency of maize in Nepal leading to increased demand for scaling

- S4I investment is fostering a market system development approach with multi stakeholder engagement to scale crop production by promoting technical and business process innovations

- S4I investment is fostering improved input and output market development leading to more efficient and profitable market systems in Nepal.

- S4I investment is targeting the change in the Government of Nepal’s (GoN) program scaling strategies with public private partnerships

- S4I investment is fostering new investments from Nepal’s Ministry of Agriculture and Livestock Development (MoALD) for scaling innovations from Western to Eastern Nepal

What is the additional outcome, component, activity that S4I is bringing to the on-going scaling process?

- Public private community partnerships in promoting market led input market system

- Scaling out the innovations from Western Nepal to Eastern Nepal, thereby reaching out the entire food basket of Nepal.

- Capacity development of stakeholders in responsible and inclusive scaling pathways

- Developing an ecosystem of private sector actors to foster innovation scaling and investment.

- Providing evidence for inclusive and resilient scaling pathways to generate donor and government investments in sustainable agrifood system development.

Annex:

  - Flagship 3 years plan

  - Flagship 2026 plan