# Meeting Notes: S4I Nepal Scaling Track Inception Meeting

Date: January 13, 2026
Time: 12:00 PM
Attendees: Dyutiman Choudhary (CIMMYT), Narayan Khanal (CIMMYT), Santosh Nepal (IWMI), Sanju Koirala (IWMI), Evan Girvetz (Alliance Bioversity-CIAT), Tim Krupnik (CGIAR), Richard Kohl (External Scaling Expert), Md. Masud Rana (CIMMYT-Bangladesh), Michael Baum (ICARDA), Khondker Murshed-e-Jahan (WorldFish), and others.

## 1. Presentation Summary

- Project Title: Market-led Partnerships for Resilient Agri-Food Systems in Terai, Nepal

- Innovation Package: Bundled interventions—improved seeds, soil fertility (4Rs, compost), mechanization, irrigation, and Multi-Stakeholder Platforms (MSPs).

- Scaling Ambition (2026):

  - Reach 39,300 rice households + 19,000 maize households

  - Cover 2,000 ha irrigated; 50,000 ha under improved inputs

  - Engage 200k consumers; create 3,000 jobs; leverage $10M

- Evidence of Success: 700% increase in spring maize area (2021–25), $3.3M in maize sales, high adoption rates of hybrids and line planting.

- Scaling Pathway:

  - Farmer/stakeholder mobilization via MSPs

  - Input market development and last-mile delivery

  - Public–Private Partnerships (PPPs) and policy alignment

- Key Partners: Farmer cooperatives, agro-dealers, seed companies, local/provincial governments, MoALD, private sector (feed mills, MSMEs).

## 2. Key Questions & Feedback from Panel

### A. Complexity & Focus

- Tim Krupnik: Concerned about the complexity of the bundle and the ambitious scope given reduced budget and one-year timeline. Recommended focusing on the most impactful components.

- Richard Kohl: Questioned the clarity of the “viable business model”—uncertain which actor(s) the model serves. Suggested a capacity analysis of scaling partners to ensure they can scale effectively.

- Evan Girvetz: Encouraged honing in on specific PPP models and outcomes achievable with S4I funding versus bilateral projects.

### B. Scaling Pathway & Evidence

- Panel: Asked for stronger evidence that the chosen scaling pathway is optimal. Suggested a more logic-model-driven approach to justify the pathway.

- Richard Kohl: Noted the need for clear incentives for scaling partners and a strategy to manage transaction costs with numerous actors.

### C. Inclusion & Equity

- Panel: Noted that while inclusive scaling is mentioned, the direct link between activities and inclusion of women, youth, and marginalized groups was not clearly articulated.

### D. Risks & External Factors

- Panel: Raised concerns about political risks (upcoming elections) and potential disruption of subsidy programs.

- Richard Kohl: Questioned whether government partners have the funding and capacity to scale effectively.

### E. Collaboration & Linkages

- Panel: Asked for concrete linkages with other CGIAR programs (e.g., Breeding for Tomorrow) and how they will be operationalized.

## 3. Responses from Nepal Team

- Dyutiman Choudhary: Acknowledged the need to simplify the bundle—likely focusing on seeds, irrigation, and soil fertility, while de-emphasizing mechanization (already covered elsewhere).

- Santosh Nepal: Highlighted ongoing PPP work in irrigation (public–private–community partnership) and the potential for “irrigation as a service” models.

- Team Commitments:

  - Revisit Gantt chart and activity plan to reduce overlaps and complexity.

  - Prioritize “low-hanging fruit” for quicker impact.

  - Strengthen focus on winter-season crops to reduce complexity.

## 4. Next Steps & Support Needs

- S4I Team will compile questions and send a summary email for a brief written response from the Nepal team.

- Nepal Team to refine scaling pathway, simplify activities, and clarify outcomes attributable to S4I investment.

- Coaching & Support: Team expressed interest in support on:

  - ROI and market assessments

  - Inclusive scaling (Area of Work 3)

  - PPP model design and capacity building

- Future Engagement:

  - Quarterly check-ins (next in April 2026)

  - Possible follow-up meeting in 2 weeks to review revised plans

  - Creation of a Teams chat for peer-to-peer learning across scaling tracks

## 5. Closing

- Meeting ended on a positive note with appreciation for the feedback.

- Nepal team committed to refining plans and leveraging S4I support for sharper, more focused implementation in 2026.

Prepared by: AI Notetaker based on transcript and slide content
Date: January 13, 2026