## 3 years
Market led partnerships for resilient agri-food systems in Terai region of Nepal
Implementation plan
Year
| Activities | 2026 | 2027 | 2028
1 | Farmer and stakeholder mobilization
1.1 | Engage and develop coodination mechanisms for scaling with provincial Governments
1.2 | Develop and strengthen multi stakeholder platforms for input market system coordination; develop input delivery and distribution strategies with public and private actors.
1.2 | Prepare inclusive and responsible road maps for seed (OPV, hybrids, local land race production, import, distribution and delivery.
1.3 | Update road maps for seed (OPV, hybrids, local land race production, import, distribution and delivery.
1.4 | Develop a strategy to apply balanced soil fertility management technologies the 4Rs (right source, right rate, right time, right place) of nutrient management
1.5 | Update the strategy to apply environmental friendly balanced soil fertility management technologies the 4Rs (right source, right rate, right time, right place) of nutrient management
1.6 | Support to develop an irrigation scheduling and plot-based water management strategy
1.7 | Review and update the irrigation scheduling and plot-based water management strategy
1.6 | Conduct farmer mobilization with focus on women and youth and orientation programs at the various sites in the 3 provinces
1.7 | Follow up trainings by cooperatives with producers
1.8 | Develop a strategy for promoting digital platforms for extension and advisories
1.9 | Review the strategy for promoting digital platforms for extension and advisories
2 | Input market development and delivery
2.1 | Support the delivery of seed, ISFM, machinery and irrigation inputs product to farmers.
2.2 | Develop and implement last mile distribution systems with public private partnerships
2.3 | Conduct training for market actors and extension workers on input delivery and extension;
2.4 | Link market actors with farmers cooperatives and large Ag development programs for supplying quality inputs throughout the cropping season.
2.5 | Support seed and machinery associations with new research and business insights for investments.
2.6 | Strengthen farmers output market linkages to creating a self-sustaining business model for ag inputs and outputs.
3 | Delivery and knowledge assisted public private-cooperative partnerships
3.1 | Conduct market assessments for crops ag inputs focussing on seed, soil fertility, ag machinery and irrigation
3.2 | Develop partnerships with donor and Government of Nepal programs for generating investments
3.3 | Conduct annual monitoring of activities with local knowledge partners such as universities and colleges.
3.4 | Organize sharing meetings and joint field vists with stakeholders for sharing and scaling interventions
3.5 | Develop capacities on use of scaling scan tool for scaling rice, maize and legumes
3.6 | Organise regional exchange and knowledge sharing visits for designing new projects and investments
3.7 | Support to organize investment forum to boost the delivery of quality ag inputs to farmers.
3.8 | Support to organize local trade fairs to boost the delivery of quality ag inputs to farmers.
3.9 | Organize policy dialogues to boost the delivery of quality ag inputs to farmers.
3.1 | Conduct detailed impact assessment of the scaling interventions

## 2026
Market led partnerships for resilient agri-food systems in Terai region of Nepal
2026 Implementation Plan
|  |  |  | Jan | Feb | Mar | April | May | June | July | Aug | Sep | Oct | Nov | Dec
1 | Farmer and stakeholder mobilization
1.1 | Engage and develop coodination mechanisms for scaling with provincial Governments | Nos | 3 | bar: Feb to April
1.1.1 | Develop and strengthen district multi stakeholder platforms for input market system coordination; | Nos | 7 | bar: Feb to Mar; June to July; Sep to Oct
1.2 | Develop input delivery and distribution strategies with public and private actors. | Nos | 3 (per province) | bar: Feb; June; Sep
1.3 | Prepare road maps for seed of target crops (OPV, hybrids, local land race, import, distribution and delivery) addressing inclusivity, sustainability and resilience. | Nos | 3 (by province) | bar: Jan to Feb
1.2.1 | Organise province level seed road map meetings with agrifood system value chain actors | Nos | 3 (by province) | bar: Jan to Feb; May; Sep
1.2.2 | Follow up with seed producers for finalizing road map | Nos | 9 | bar: Mar; June; Oct
1.3 | Develop a strategy to apply balanced soil fertility management technologies the 4Rs (right source, right rate, right time, right place) of nutrient management | Nos | 4 (1/crop)
1.3.1 | Conduct TOTs on technology bundles with extension agents and lead farmers. | Nos | 3 | bar: Feb; June; Sep
1.3.2 | Conduct ToTs on ISFM with cooperatives and extension workers | Nos | 3 | bar: Feb; June; Sep
1.3.3 | Co-design and distribute technlogy bundles and cropping calendars to stakeholders through physical and digital means | Nos | 4 crops | bar: Feb; June; Oct
1.4 | Prepare a water supply, irrigation equipment and machinery delivery strategy for efficient use and delivery at key crop stages. | Nos | 3 (province wise) | bar: Feb to Mar; June; Oct
1.5 | Co-design with stakeholders an irrigation scheduling and plot-based water management action plan for scaling technology bundles | Nos | 4 crops | bar: Feb to Mar; June; Oct
1.6 | Develop cooperative level production plans with various category of farmers and inclusive technology delivery strategies | bar: Feb to Mar; June; Oct
1.7 | Conduct farmer mobilization and orientation programs at the various sites in the 3 provinces | Nos | 21(7x3) | bar: Feb to Mar; June to July; Oct to Nov
1.7.1 | Follow up trainings by cooperatives with producers | Nos | 21 | bar: Feb to April; June to Aug; Nov to Dec
1.8 | Develop a strategy for promoting digital platforms for extension and advisories | Nos | 1 | bar: Feb to Mar
2 | Input market development and delivery
2.1 | Support to implement the roadmaps for delivery of seed, ISFM, machinery and irrigation inputs product to farmers | Nos | 4 (per crop)
2.2 | Develop and implement an inclusive and last mile input distribution system with public private cooperative partnerships | Nos | 4 (per crop) | bar: Feb to May; July to Aug; Oct to Dec
2.3 | Conduct training for market actors and extension workers on gender responsive, inclusive and sustainable input delivery and extension | Nos | 3 (1/province) | bar: Mar; Aug; Nov
2.4 | Link market actors with farmers cooperatives and large Ag development programs for supplying quality inputs throughout the cropping season. | Nos | 21 MSMEs | bar: Mar to Dec
2.5 | Support seed and machinery associations with new evidence and business case for investments. | Nos | 2 | bar: Mar to June
2.6 | Strengthen farmers output market linkages to create a self-sustaining business model for ag inputs and outputs. | Nos | 2 (maize and rice) | bar: April to May; Oct to Nov
2.6.1 | Organise meeting between producers and buyers for facilitating purchase agreements | Nos | 2 (Maize and rice) | bar: April to May; Oct to Nov
3 | Delivery and knowledge assisted public private-cooperative partnerships
3.1 | Conduct market assessments for crops ag inputs ( status, emerging changes, opportunities and challenges) focussing on seed, soil fertility, ag machinery and irrigation | Nos | 4 (per sector) | bar: April to Oct
3.2 | Develop partnerships with donor and Government of Nepal programs for generating investmentsfor inclusive and responsible scaling. | Nos | 30
3.3 | Conduct annual monitoring of activities with local knowledge partners such as universities and colleges. | Nos | 1 | bar: Oct to Nov
3.4 | Organize sharing meeting and joint field vists with stakeholders for sharing and scaling interventions | Nos | 1 | bar: Oct to Nov
3.5 | Partcipate in local, provincial and national events to share scaling potential for ag inouts for generating investments | Lumpsum
3.6 | Develop capacities on use of scaling scan tool for scaling rice, maize and legumes | Nos | 2 (west and East)
3.7 | Support to organize investment forum to boost the delivery of quality ag inputs to farmers. | Nos | 3 (per province) | bar: April to June