Meeting Minutes

Date: January 28, 2026
Time: 1:26 PM
Subject: Review of Scaling Solution Track - Direct Seeded Rice (DSR) & Mechanization in Eastern Uttar Pradesh
Attendees: Evan Girvetz, Suryakanta Khandai, Rica Joy Flor, Marcel Gatto, Sudhanshu Singh, Richard Kohl, Vikram (IRRI-IN), Others from IRRI & S4I team.
Apologies/Left Early: Richard Kohl (dropped off during meeting)

1. Purpose & Introduction

- Meeting convened to review the proposed scaling solution track for DSR and complementary mechanization services in Eastern Uttar Pradesh (UP), India.

- IRRI team (Suryakanta, Vikram, Sudhanshu) presented the approach, which is nested within the larger bilateral "UP ADDRESS" government project.

2. Presentation Summary (IRRI Team)

- Goal: Scale DSR and mechanization (Zero-Till Wheat, Happy Seeder) to improve productivity, profitability, and sustainability.

- Core Strategy: Cluster-based demonstrations (15-20 ha), Farmer Producer Group formation, and strengthening the service economy through Custom Hiring Centers (CHCs).

- Key Activities: Training master trainers & mechanics, leveraging government schemes for machinery, facilitating access to seeds/herbicides, and providing technical support.

- Targets: Contribute to a broader goal of 1 million hectares by 2028 through direct project targets (e.g., ~90,000 farmers/hectares initially) and indirect influence via partners (e.g., Bayer).

- S4I Funding Role: Proposed to add value through enhanced technical support, capacity building for partners, funding for critical demonstrations (herbicides, new varieties), and enabling a faster, more sustainable scaling model.

3. Key Questions, Comments & Responses

A. Clarification on Scaling Model & Drivers (Richard, Marcel)

- Q: Who is the main driver for scaling? Is it machinery companies, the government, or IRRI?

- A: The Government of UP (UP DAS) is the lead implementing agency. IRRI is the technical partner responsible for achieving specific scaling deliverables and providing expertise. Machinery manufacturers from Punjab/Haryana are being engaged to establish local dealerships for availability.

- Q: What is the additionality of S4I funding if scaling is already happening via the bilateral project?

- A: S4I enables:

  - Deeper Support: More expert time for training, capacity building, and technical backstopping.

  - Enhanced Demonstrations: Funds for critical inputs (e.g., herbicides, new herbicide-tolerant seed varieties) to ensure demonstration success.

  - Accelerated Model: A focused "cluster" approach to create visible hubs of success that attract and convince more farmers organically.

  - Systemic Strengthening: Training for partner staff (e.g., from ITC) to amplify scaling efforts.

  - Future Innovations: Laying groundwork for integrating carbon credit incentives and stronger policy dialogue, which are not part of the core government project.

B. System Gaps & Risks (Richard)

- Q: How are critical supporting services like spare parts, repairs, and financing being addressed?

- A: The project includes plans to:

  - Establish spare part banks at the district level.

  - Train local mechanics and machine operators in repair and maintenance.

  - Engage machinery companies to set up local dealerships/service networks.

  - CHCs are intended to be the sustainable business entities providing and maintaining services.

- Q: What about partial adoption of the complex DSR package and the risk of weed resistance to herbicides?

- A: The cluster-based, group approach with continuous technical monitoring is designed to improve fidelity. The team acknowledged the risk of weed resistance and is planning to introduce herbicide-tolerant varieties as part of the strategy. Continuous monitoring is deemed critical for success.

- Q: Has political economy risk, such as labor displacement, been considered?

- A: Initial piloting has not encountered significant resistance, largely due to high out-migration and labor scarcity in the region. The point was acknowledged as important for ongoing monitoring.

C. Measurement, Inclusion & Learning (Marcel, Richard)

- Q: Profitability for whom will be measured?

- A: Primary focus is on farmer profitability. Secondary data will be collected on the turnover and profitability of Custom Hiring Center operators.

- Q: What activities ensure inclusive scaling for women, youth, and smallholders?

- A: The cluster formation protocol mandates that 80-90% of participants are small/marginal farmers and 10-30% are women farmers.

- Q: How will adoption and impact be verified for learning?

- A: A baseline has been collected under the UP ADDRESS project. Seasonal data collection is planned, with an endline assessment scheduled for late 2026 to verify adoption rates and outcomes.

D. Strategic Scale & Coordination (Richard, Marcel, Inga via chat)

- Q: How does the model move from linear, project-driven expansion to self-propelling market scale?

- A: The pathway focuses on creating a sustainable "service economy" via CHCs and trained entrepreneurs. Training-of-trainers and empowering partner institutions (e.g., input suppliers) are key mechanisms.

- Clarification Needed: Discrepancy noted between large vision targets (1M ha) and direct project targets (~90K). Requires future alignment.

- Cross-CGIAR Linkage: Area of Work 3 (Enabling Environments) offered to connect and provide comparative analysis on enabling environment barriers across similar mechanization tracks.

4. Action Items & Next Steps

| Item | Responsible Party | Deadline/Note |
| --- | --- | --- |
| 1. Revise presentation slides incorporating feedback and clarifications. | IRRI Team (Suryakanta, Vikram) | ASAP / Mid-February |
| 2. Develop a refined Scaling Solution Track Profile for S4I documentation. | Area of Work 2 & IRRI Team | Based on revised slides |
| 3. Schedule follow-up on evaluation plans and learning studies. | Area of Work 5 (Marcel) & IRRI Team | To be scheduled |
| 4. Coordinate on enabling environment support and linkage with other mechanization tracks. | Area of Work 3 (Inga) & IRRI Team | To be scheduled |
| 5. Next quarterly check-in for this scaling track. | All | April 2026 |

5. Closing

- Meeting concluded with thanks. Participants recognized the need for continued refinement and collaboration across S4I's different work areas to strengthen the scaling plan.

- The IRRI team is to submit revised materials to facilitate the next steps in the S4I process.