# Scaling Track 2.3 – Forage-Based Livestock Feed Innovations

Lead Center: ILRI

Countries: Ethiopia, Zambia

Flagship Alignment: AoW2 Flagship 2.3 – Delivering Sustainable Animal and Aquaculture Genetics, Inputs, and Services

PoD Target (2026): 53,234 smallholder farmers adopting forage-based innovations (Center Decision Letter target)

Current Slide Target (2026): 20,000 reached; 14,000 applying innovations

## Current Situation: Multiple years of validation (Africa RISING, SAPLING, Mixed Farming Systems); demonstrated productivity and income gains in Ethiopia and Zambia; Scaling Readiness: 6 (Ethiopia), 8 (Zambia); IPSR packaging completed. Technology validation is not the binding constraint.

## 2. Key Limiting Factors

### Ethiopia – Market Distortion

- Indiscriminate free forage seed distribution by government undermines private seed market development (primary factor)

- Weak commercial incentives for private seed enterprises

- High transaction costs (bulky forage biomass)

- Limited formalization of seed market channels

### Zambia – Thin Commercial Ecosystem

- Key structural constraints:

- Fragmented forage/feed enterprise ecosystem

- Weak SME financing integration

- Limited regulatory formalization

- Dependence on projects rather than commercial models

- The slides position “registered feed diets” and feed industry concepts as S4I’s unique value add, but operational details are not yet fully specified.

## The Scaling Question to Be Answered: What institutional or market rule must change within 24 months to enable self-sustaining forage input and feed markets?

Specifically:

- Ethiopia: Can government policy shift from free seed distribution to structured, market-based seed systems?

- Zambia: Can forage-based feed rations be formalized and commercialized in a way that unlocks SME finance and market demand?

## Existing Bilaterals: AICCRA (Feed gap bridging, forage seed systems); TAAT (Seed multiplication, capacity building); UNIQUE, SNV (Fodder promotion); ESLIP (EU) – Forage scaling; JSL (World Bank; Legume promotion)

Existing bilaterals already cover agronomic validation, extension training, demonstrations, seed multiplication, advisory services, and stakeholder engagement. If S4I primarily funds additional training, coordination platforms, Living Labs, or advisory refinement, duplication risk will be moderate to high.

S4I Additionality: Slide deck positions additionality as: “Mainstreaming bilateral works into a national scaling strategy.” This is coherence-building additionality.

However:

- It is coordination-focused, not rule-changing.

- It does not yet specify institutional reform milestones.

- It lacks clearly defined exit criteria.

To justify S4I engagement, additionality must move beyond alignment toward structural unlock.

## Core Strategic Questions

- What is the binding constraint in each country?

- Which constraint can realistically shift in 24 months?

- What defines institutional success?

- Which partners are truly catalytic vs. supportive?

- How does this reach 53,234 adopters in 2026?

- What defines S4I exit?

## Risk Assessment Summary

The track is scientifically strong but structurally diffuse.

The central risk is breadth without prioritization.

Without identifying one catalytic lever per country, impact may remain incremental.

# Overall Strategic Position

Strengths

- Strong evidence base

- High livelihood impact potential

- Clear productivity gains

- Strong ILRI leadership

Concerns

- Diffuse intervention package

- Coordination-heavy additionality

- No clearly defined institutional milestone

- Target recalibrated to budget rather than leverage

# Bottom Line

This is a scientifically robust and high-potential track.

However, to be positioned as a true scaling engine within S4I, it must:

- Sharpen the binding constraint in each country

- Identify a key catalytic reform per country

- Clarify finance integration

- Reduce breadth and prioritize leverage

- Define a 2026 institutional success trigger