Scaling Track: Barley–Wheat Balady Bread (Egypt)

Current status: Technical feasibility has largely been demonstrated through agronomic trials, milling and baking pilots, nutrition evidence, stakeholder workshops However, technical readiness is not the binding constraint.

Key Limiting Factor: Scaling depends on institutional integration into Egypt’s wheat subsidy and procurement system. Specifically, barley blending must be normalized within procurement specifications, milling and baking standards, subsidy reimbursement formulas and quality and compliance mechanisms.

Scaling question to be answered: What changes in procurement standards, subsidy reimbursement rules, milling specifications, and accountability systems are required for barley–wheat blending to become normal within the Balady system?

Current and prior bilaterals are running pilots and demonstrations, producing nutrition and climate evidence, convening stakeholders, and issuing policy briefs. These activities are good, but more is needed for systemic scaling.

However, bilaterals are not redesigning subsidy mechanisms, aligning cross-ministerial incentives, managing political economy risk, and institutionalizing blending standards

Key concerns:

- Risk of Perpetual Pilots: further demonstrations will not change procurement.

- S4I Value Proposition: If S4I focuses on evidence or pilots, duplication risk is high.

- Political Economy Sensitivity; Balady bread is politically charged; perceived quality shifts carry reputational risk;

- Exit Plan: Lack of clarity on milestone defining when S4I’s role is complete

- Institutional Owner: Multiple ministries are involved; no single accountable integrator.

Examples of the types of activities S4I could be doing

- Designing phased integration into procurement standards

- Supporting cross-ministerial alignment and coordination

- Structuring risk-sharing mechanisms during transition

- Clarifying measurable institutional reform milestones

- Defining explicit exit criteria

Examples the types of activities that S4I should probably not be doing:

- Fund additional pilots

- Expand geographic testing

- Operate as a technical delivery project

Core Strategic Questions to discuss in next meeting:

- What is the binding constraint -- What specific institutional rule/policy/process must change within 24 months for barley blending to scale—and is the S4I scaling track structured to change it?

- Does the current S4I budget allocation support system reform — or primarily project activity? What defines successful “exit” from S4I support?

- How long are you going to continue long term sustainability without donor support after 2028?