SCALING INTELLIGENCE ASSESSMENT

& Richard Kohl Coaching Preparation

Solution Scaling Track: Potato Zero Tillage and Mulching (PZTM) — India

Scaling for Impact Science Program · Area of Work 2 · International Potato Center (CIP)

Prepared by the Scaling Intelligence Operating System

Scaling Librarian · Scaling Analyst · Scaling Strategy Coach (collaborative, perspectives preserved)

Blind, evidence-based assessment · Version 1.0 · 14 July 2026

## Reading conventions

[Evidence] directly supported by supplied source material. [Interpretation] reasoned synthesis across sources. [Strategic Judgement] expert scaling judgement. [Recommendation] proposed action. [Unknown] insufficient evidence to judge.

Confidence levels: Well supported · Moderately supported · Emerging · Speculative · Insufficient evidence.

Discipline markers: where the Librarian (L), Analyst (A) and Strategy Coach (SC) diverge, the disagreement is preserved rather than resolved, per operating instructions.

Source base: (1) S4I AoW2 Expression of Interest [EoI]; (2) Flagship Solution Scaling Track Profile v1.0, Feb 2026, reviewed 27/05/2026 [Profile]; (3) Inception Feedback / prior review [Feedback]; (4) Inception Meeting script/transcript, 26.01.2026 [Meeting]; (5) Inception presentation deck [Slides]. No external data were introduced; this is a blind assessment of the supplied evidence base.

# Contents

# 1. Executive Summary

### Executive judgement (Strategy Coach)

Stage-gate classification: TRANSITION TO SCALE — funded conditionally and narrowly as bottleneck-resolution and delivery-system de-risking, NOT as active scaling or as general co-financing of delivery.

One-sentence rationale: The agronomic and farmer-level case for PZTM is strong and rigorously evidenced, but there is no evidence yet that any actor other than CGIAR and its donors will deliver, finance and sustain the practice at state scale, so the binding question is a scaling-system question, not a technology question.

Most upstream weakest link: the absence of an actor-driven delivery-and-financing system — no public, private or community actor yet has a demonstrated incentive and business/fiscal case to deliver and pay for PZTM without ongoing CGIAR facilitation.

### What is genuinely proven

[Evidence] PZTM produces real, measured farmer benefits. An RCT across 200 villages / 2,000 households in Bihar plus multi-site trials show higher gross margins, lower production costs, reduced pest and disease incidence, ~50% fewer irrigation events, and positive gender outcomes (increased joint decision-making). The core practice sits at Scaling Readiness Level ~7 and works under real farmer conditions in the manual model. This is a technically mature innovation with an intuitive farmer value proposition.

### What remains assumption, not fact

- Delivery beyond facilitation: ~7,750 verified adopters were reached over ~4 years entirely under GIZ-funded CGIAR/Digital Green/JEEViKA facilitation. There is no evidence that adoption continues, or accelerates to the 35,000–50,000 ambition, without that facilitation.

- Institutional embedding: The Bihar Department of Agriculture has invited a scaling proposal — a genuine signal — but there is no signed MoU, no budget line, and no formal adoption into extension manuals. Invitation is being treated as readiness.

- Mulch (rice straw) at scale: Straw is a competing livestock feed; combine harvesting reduces its availability. The EoI explicitly assumes straw availability 'will not be a key challenge during the current scaling phase' — an assumption every reviewer implicitly challenged.

- Market pull and payer demand: Processor interest (PepsiCo, McCain, SAI Platform) is exploratory; no sourcing contract or price premium exists. Output-market absorption and cold-storage capacity for a large potato-area expansion are unexamined.

- Financial sustainability: The founding GIZ/BMZ bilateral closed at end-2025; SAI Platform is the only remaining linked funder; no S4I grant figure appears in any document; carbon revenue (~$21.6/ha) is unrealised.

### The three converging reviewer critiques

[Evidence] The Inception Feedback, the Meeting transcript (Girvetz, Krupnik, Flor) and the S4I framing all pushed on the same three points: (1) the 2026 plan lists 20+ activities with no prioritisation ('operationally busy without being structurally catalytic'); (2) the primary scaling pathway is not declared or evidenced; and (3) there is no evidence PZTM scales through business or institutional models rather than continued facilitation. The team openly acknowledged the EoI 'received the least scoring' and is 'not as strongly embedded in an ongoing bilateral or government program as of now.'

### Headline recommendation

[Recommendation] Fund one more year, conditionally. Re-scope the track from 'scaling PZTM' to 'building and de-risking the delivery-and-financing system that a public, private or community actor will own after donors leave.' Require the team to (a) declare one primary pathway, (b) produce actor-specific business/fiscal cases showing who earns, who pays, who bears risk and who continues, (c) convert the Bihar invitation into a costed MoU, and (d) reconcile its conflicting evidence base into one defensible fact sheet. Defer certification/NFT/carbon and mechanization until a binding constraint is shown to depend on them.

# 2. Scaling Knowledge Summary (Librarian)

This section organises the supplied evidence base, preserves provenance, classifies evidence types, and flags conflicts, cited-but-unsupplied evidence, and gaps. It distinguishes what documents assert from what is actually observed.

## 2.1 Key knowledge objects and provenance

| Knowledge object | What it is | Evidence type | Provenance / status |
| --- | --- | --- | --- |
| PZTM core practice | Early-maturing potato tubers placed on unploughed rice-fallow, covered with rice-straw mulch; enables immediate planting, conserves moisture, suppresses weeds | Validated agronomic innovation (SRL ~7) | Profile, EoI, Slides; peer-reviewed papers cited |
| Bihar RCT | 200 villages / 2,000 households measuring PZTM impact | Randomised controlled trial | EoI, Profile, Meeting — described but the RCT itself is not in the reference list and appears unpublished/unsupplied |
| Delivery model | Digital Green video-mediated extension bundled with JEEViKA women's SHGs; Farmer.Chat AI advisory | Model + external adoption evidence | Profile, Slides; DG efficacy cited from Ethiopia/Uganda (Abate 2023; Van Campenhout 2021) |
| Gender study | Digital Green (2024) gender dynamics study, Bihar | Observational study | EoI, Slides — referenced, not supplied |
| Pest/disease reduction | 30–40% lower pest & disease incidence, on-station and on-farm | Trial evidence | Meeting: 'we will submit for publication next month' — NOT yet published |
| IPSR / Scaling Scan / GenderUp outputs | Readiness & risk profiling; SRL≥7; straw access 'low', mechanization 'moderate' | Structured self-assessment | EoI — responsible-scaling sub-section disclosed as LLM-generated, human-verified |
| 2026 activity portfolio | 20+ activities across delivery, policy, digital, mechanization, certification | Plan / intention | EoI, Slides, Meeting |
| PZTM production manual | Kakraliya, Gatto, Ramírez, Kreuze & Kumar (2024) | Peer-reviewed / DOI | Slides, EoI reference list |

## 2.2 Evidence classification (technical vs scaling)

[Observed] Strong, multi-source evidence for technical efficacy and farmer-level profitability under real conditions (RCT + multi-country trials + manual).

[Observed] Evidence for the delivery mechanism's ability to raise adoption is largely borrowed from Digital Green's efficacy in other crops/countries (SRI in Bihar; Ethiopia; Uganda), not from PZTM-specific scaling evidence.

[Unknown] No independently validated evidence exists for scaling through business or institutional models without CGIAR facilitation, for sustained (multi-season, unfacilitated) adoption, or for deep-scaling outcomes at scale — the team states these will have to be assumed for 2026, not measured.

## 2.3 Cross-document inconsistencies (conflicting evidence log)

[Evidence] The same headline facts differ materially across documents. This is a knowledge-integrity problem the team must resolve before coaching; it undermines the credibility of an otherwise strong evidence base.

| Metric | Conflicting values across sources | Note |
| --- | --- | --- |
| Gross margin gain | +16% (Profile) vs '60% higher gross margin' (Meeting) | ~4x discrepancy; likely transcription error but unreconciled |
| Yield gain | ~5% (Profile, Meeting) / ~14% / ~10–15% / 'up to 20–30%' / '3–4x in Bangladesh' (EoI) | Range spans an order of magnitude across geographies |
| Cost reduction | −31% (Profile) / −24% / −25–30% / −25% (EoI) | Depends on baseline; not standardised |
| Verified adopters | ~5,000 (EoI) / ~7,750 (Profile, Feedback) / ~8,000 (Meeting) / 'a few hundred in 4 districts' (EoI) | Four different figures |
| 2026 household target | 10,000 (EoI/Profile) vs 35,000 (Meeting) | 3.5x difference in headline ambition |
| GIZ bilateral start | Oct 2021 (EoI) vs 'started 2022' (EoI) vs 150 adopters in 2022 (Meeting) | Timeline inconsistent |
| IGP potato households (denominator) | 6–7 million (EoI/Slides) — disputed in Meeting as 'much higher; that number in Bangladesh alone' | Denominator itself contested |

## 2.4 Cited-but-unsupplied evidence

- The Bihar RCT (200 villages / 2,000 households) — central to the case, described but neither published nor supplied.

- The pest/disease (30–40%) study — 'to be submitted for publication.'

- Digital Green (2024) gender study; the PZTM Gender Strategy (GIZ/CIP).

- The draft scientific manuscript submitted to the Department of Horticulture; the detailed project budget; Africa maize-system trial data; potato demand projections (promised in Meeting, not provided).

## 2.5 Evidence gaps (what is simply absent)

- Any S4I grant amount or budget figure — absent from all five documents.

- Actor-specific business/fiscal cases (who earns, who pays, who continues).

- Output-market and cold-storage absorption analysis for expanded potato area.

- Sustained/unfacilitated adoption and disadoption data.

- A political-economy / stakeholder analysis (recommended by reviewers, not yet done).

## 2.6 Librarian recommendations (repository)

[Recommendation] Create Knowledge Cards for: PZTM core practice; the Bihar RCT (with a 'source not supplied' flag); the DG+JEEViKA delivery model; and the 2026 activity portfolio. Open a 'Conflicting Evidence' record (Section 2.3) and a 'Cited-but-Unsupplied' register (Section 2.4). Tag the EoI responsible-scaling section as LLM-generated for provenance. Do not treat any headline figure as canonical until reconciled.

# 3. Scaling Intelligence Assessment (Analyst + Strategy Coach)

## 3.1 Scaling ambition and denominator

[Evidence] Stated ambition: 10,000 households / 5,000 ha in Bihar in 2026 (Profile/EoI) — the Meeting cites 35,000 households; long-term 50,000+ households (50% women), 10,000+ ha, 1,000+ women promoters, $2M+ leveraged. Denominator: Bihar ~800,000–900,000 potato households on ~0.4 ha average; Indo-Gangetic Plains stated as 6–7 million households on 2M ha (disputed as too low).

[Interpretation] The ambition is appropriately bold against a real denominator — a modest pilot would not matter. But it is not yet disciplined: the target conflates 'households reached' with sustained, high-fidelity adopters. Reaching 7,750 over four years of facilitation and then declaring 35,000–50,000 requires a step-change in the delivery mechanism that is asserted, not evidenced.

[Recommendation] Recast the ambition around four nested metrics — reach, trial, effective (minimum-viable-package) adoption, and sustained system adoption (multi-season, reduced-subsidy). Report against all four, not a single headline household count.

## 3.2 Theory of scaling

[Evidence] The ToC (Profile 3.2) is: IF farmers gain access to the PZTM bundle through trusted networks (JEEViKA/Digital Green) and government extension, AND systemic barriers (straw, mechanization, institutional recognition) are addressed through partnerships and policy, THEN farmers adopt at scale, leading to lower costs, higher incomes, better soil — a systemic shift to climate-smart agriculture with women central.

[Strategic Judgement] This is an activity-and-access theory of change, not an actor-driven one. It describes conditions to be created but not who has the incentive to create and sustain them. Following Kohl's pattern: a credible ToC works backward from the constraint through the actors who profit, invest, coordinate, deliver and continue after donor support. As written, the ToC's verbs ('are addressed', 'gain access') have no owner. Confidence that this ToC is scaling-ready: Emerging at best.

## 3.3 Innovation package and adoptability

[Evidence] The bundle is: (a) early-maturing potato variety + zero-tillage + rice-straw mulch; (b) digital/community extension (DG video via SHGs + Farmer.Chat); (c) institutional & market linkages (extension manuals, mulch supply, processor engagement, certification). Diversifying options named: mechanization, apical rooted cuttings (seed), DSR–PZTM systems, circular economy. The model as evidenced is entirely manual (confirmed in Meeting).

[Interpretation] Adoptability is high for smallholders precisely because the model is labour-saving and manual. This is also its scaling ceiling: the EoI concedes the labour advantage disappears under mechanised cultivation and 'has less incentive' for larger farmers. The bundle is well-formed agronomically; its adoptability at scale depends on components (mulch supply, seed, cold storage) that are weakest.

## 3.4 Actor map and incentive structure

[Evidence] Principal actors and stated roles:

- CIP: technical leadership, agronomic backstopping, MELIA (coordinator today).

- Digital Green: video-mediated extension, Farmer.Chat AI, trains JEEViKA staff.

- JEEViKA (Bihar Rural Livelihoods Promotion Society): last-mile access via women's SHGs and Village Resource Persons; expected to mentor 1,000+ women promoters.

- Bihar Dept. of Agriculture & Horticulture: chairs the proposed State PZTM Coordination Committee; mainstreaming into extension; funding pathway from 2026 if approved.

- PepsiCo / McCain / SAI Platform: exploratory PPP/private pathway; agronomic validation; possible contract sourcing.

- IRRI (DSR, region ID), CIMMYT (learning), GIZ (policy/carbon/mechanization broker), Sheet Profile + Odisha Univ. (mechanization prototype), World Bank (early discussions), NEWS/FPOs (delivery, aggregation).

[Strategic Judgement] The incentive map is the weakest part of the design. The named lead partners (CIP, DG) are knowledge-push actors, as Rica Flor observed in the Meeting: 'the key partners are really knowledge partners… what is incentivizing JEEViKA to do more than just give the knowledge?' JEEViKA's VRPs are paid 'very little'; the incentive is female leadership, not a business case. No actor in the map yet has a demonstrated financial incentive to deliver PZTM at scale and pay for it after donors leave. This is the crux of the whole assessment.

## 3.5 Scaling system map

| Function | Actor(s) | Incentive strength | Risk |
| --- | --- | --- | --- |
| Demand creation | DG/JEEViKA (farmers); DoA (institutional) | Moderate (farmer) / Emerging (institutional) | Reach ≠ sustained adoption; disadoption without facilitation |
| Delivery | DG video + JEEViKA SHGs; govt extension (aspirational) | Weak — no paid delivery agent; VRPs paid nominally | No delivery actor with a business/fiscal case post-donor |
| Input supply (mulch, seed) | Unassigned; 'straw banks'/youth micro-enterprise proposed | Weak / unproven | Straw competes with fodder; seed & cold-storage gaps |
| Financing | GIZ (closed 2025); SAI Platform; Bihar state (if approved); S4I (amount unstated) | Weak — donor-dependent, no committed state budget | GIZ exit leaves a hole; carbon revenue unrealised |
| Coordination | CIP/CGIAR today; State Committee (proposed) | Weak — CGIAR still central | Coordination not yet transferred to a durable owner |
| Policy support | Bihar DoA/DoH; State Agri Road Map 2023–28 | Emerging — invitation, no MoU/budget | Political-economy analysis not done; burning less salient in Bihar |
| Learning/adaptation | CIP MELIA; quarterly + mid-year reviews; GenderUp | Moderate | Deep-scaling outcomes to be assumed, not measured, in 2026 |

## 3.6 Demand analysis (five demands, kept separate)

| Demand type | Evidence | Confidence |
| --- | --- | --- |
| User (farmer) demand | RCT profitability; ~7,750 adopters — but all under facilitation; disadoption flagged without intervention | Moderately supported |
| Market (output) demand | Potato output market / price absorption unexamined; 'only so many potatoes a household can eat' (Kohl, Meeting); cold-storage saturation risk | Insufficient evidence |
| Payer demand (who funds delivery) | No paid delivery model; JEEViKA VRPs nominal; S4I 'doing the heavy lifting' | Speculative |
| Institutional (govt) demand | Formal invitation to submit scaling proposal; Road Map alignment; 'strong signals' — but no MoU/budget | Emerging |
| Policy demand | Bihar Agricultural Road Map 2023–28 prioritises climate-smart ag & residue mgmt; minister 'harvesting day' | Emerging |

[Interpretation] The team's case rests almost entirely on user demand and implicitly assumes it propagates to market, payer, institutional and policy demand. It does not. The Meeting reviewers were explicit: profitability evidence is strong; evidence that PZTM scales through markets or institutions rather than facilitation is absent. Also unresolved (Kohl/Meeting): potato-vs-rice market and policy incentives are not articulated — is there structural demand for farmers to expand potato area, or is profitability alone assumed to drive the shift?

## 3.7 Delivery, financing, institutional ownership, policy

[Evidence] Delivery today is CGIAR-facilitated DG+JEEViKA. Financing: the GIZ/BMZ i4Ag bilateral (Oct 2021–Dec 2025) has closed; SAI Platform is the only remaining linked funder; no S4I grant figure is stated; Bihar state funding is contingent on proposal approval; carbon (~$21.6/ha; ~$1M at 50,000 ha) is unrealised. Institutional ownership: proposed State PZTM Coordination Committee and manual integration — none formalised. Policy: alignment asserted, no instrument yet.

[Strategic Judgement] This is the signature pattern Kohl flags: strong technology, moving institutional interest, but delivery, financing and ownership remain project-dependent. The closure of GIZ at end-2025 with no successor bilateral is the single most consequential fact in the financing picture and was openly acknowledged by the team.

## 3.8 Additionality test

[Strategic Judgement] PZTM builds on an existing platform (the GIZ/BMZ i4Ag bilateral + Digital Green + JEEViKA). The additionality of S4I must therefore be isolated from what the platform already proved.

| Category | What belongs here |
| --- | --- |
| Already proven (existing platform) | PZTM agronomy & farmer profitability (RCT, trials); DG video-mediated extension efficacy (other crops/countries); ~7,750 adopters reached under GIZ-funded facilitation; the manual delivery model |
| New under S4I (claimed) | Transition from facilitation to institutional/market embedding; PPP consortium (PepsiCo–GIZ–CIP); Farmer.Chat AI extension; certification/NFT/carbon registry; mechanization prototype; strategic prioritisation |
| Evidence that applies ONLY to the platform | All impact and adoption evidence to date — generated under continuous donor-funded CGIAR/DG/JEEViKA facilitation; none demonstrates self-sustaining scaling |
| Evidence actually supporting S4I additionality | Essentially none yet. Institutional embedding, market pull and financing leverage are aspirations, not demonstrated outcomes |

[Recommendation] Do not let the platform's agronomic evidence validate the scaling claim. S4I's defensible additionality is disciplined scaling intelligence and bottleneck de-risking — actor business cases, delivery-cost economics, adoption-fidelity measurement, institutional financing negotiation — not more delivery or more trials. S4I must state explicitly what would NOT happen without its funding.

## 3.9 Weakest-link analysis

[Strategic Judgement] Multiple candidate binding constraints were evaluated:

| Candidate constraint | Upstream/down | Who performs / who pays / who continues | Binding? |
| --- | --- | --- | --- |
| Delivery-and-incentive system (no actor with a business/fiscal case to deliver & sustain PZTM without CGIAR) | Most upstream | Today: CGIAR/DG facilitate; no one pays post-donor; no durable owner | PRIMARY — dominates the others |
| Mulch (rice-straw) supply at scale | Midstream (input) | Unassigned; 'straw banks'/youth proposed; farmers pay via saved cost | Co-binding, but solvable if an actor has incentive to solve it |
| Institutional embedding in Bihar extension | Upstream (governance) | DoA to mandate; extension officers deliver; state to fund — none committed | Necessary, not sufficient (extension systems under-resourced) |
| Seed system + cold storage | Midstream | CIP/state; farmers/market | Important; localised; not yet the binding statewide constraint |
| Output-market absorption / price | Downstream | Market/processors; farmers bear price risk | Unknown — unexamined; could bind at scale |
| Strategic prioritisation itself | Meta | Team | Real, but a symptom of the missing pathway logic |

### Anti-legibility check

[Strategic Judgement] The most legible, measurable constraint is mulch access — a clean, quantifiable input problem, which is exactly why the documents and reviewers gravitate to it (you can pilot a straw bank and count bales). The anti-legibility check asks whether the true binding constraint is something less legible. It is. Even if mulch were fully solved, there would still be no actor with the incentive and business/fiscal case to deliver PZTM to hundreds of thousands of farmers and pay for that delivery after donors exit. Mulch is a symptom-level, downstream-of-incentive constraint; the delivery-and-incentive system is the upstream cause. Solving the legible problem first would produce motion without scale.

### Selected weakest link and why it dominates

[Strategic Judgement] The single most upstream constraint is the absence of an actor-driven delivery-and-financing system. It dominates because: (1) mulch, seed and cold-storage constraints are only solved if some actor has an incentive to solve them — that incentive is what is missing; (2) institutional embedding into extension manuals is necessary but insufficient, because public extension systems are typically under-resourced and default to one-way dissemination (Kohl's own two-pager); and (3) prioritisation problems are downstream of not having decided who drives scale. Until the delivery-and-incentive question is answered, every other fix is premature.

### Preserved disagreement between disciplines

Librarian (L): the documents themselves assert the primary constraints are institutional embedding + structured mulch access (Feedback; EoI). This is what the evidence base says on its face.

Analyst (A): across all sources the recurring, unresolved constraint is the facilitation-to-system transition — 'no evidence PZTM scales through business or institutional models rather than continued facilitation.' The Analyst locates the constraint at the system-transition level.

Strategy Coach (SC): locates it one layer deeper, in actor incentives and business/fiscal cases — who earns, who pays, who continues. The SC view treats mulch and institutional embedding as co-binding but subordinate.

[Interpretation] These are nested rather than contradictory: L names the visible constraints, A names the system gap they sit within, SC names the incentive root beneath both. The disagreement worth preserving is on sequencing — L/team would fund a mulch mechanism and manual integration now; SC would first force the actor-and-business-case question and fund mulch only once an actor with an incentive to use it is identified.

## 3.10 Sustainability analysis

| Dimension | Assessment | Confidence |
| --- | --- | --- |
| Technical | Strong; SRL ~7; RCT + trials; manual model robust — but mechanised model unproven (no prototype) | Well supported |
| Financial | Weak; GIZ closed; no committed successor; no S4I figure; carbon unrealised; delivery costs unfunded post-donor | Speculative (unsustainable as configured) |
| Institutional | Emerging; invitation but no MoU, budget line or formal adoption | Emerging |
| Ownership | Weak; CGIAR/DG still central; JEEViKA incentive unclear | Speculative |
| Incentive | Weak; no actor-specific business case; private interest exploratory | Insufficient evidence |
| Political | Emerging–moderate; Road Map alignment, ministerial interest — political-economy analysis not done | Emerging |

## 3.11 Critical assumptions

| Assumption | Evidence for it | Risk if wrong |
| --- | --- | --- |
| Farmer profitability will drive scale without ongoing facilitation | RCT profitability; adoption to date | High — all adoption so far is facilitated; disadoption likely |
| Public extension will carry delivery at state scale | Road Map alignment; invitation | High — extension systems under-resourced; one-way dissemination |
| Rice straw is available at scale ('not a key challenge this phase') | Asserted in EoI; readiness rated 'low' in IPSR | High — competes with fodder; combine harvesting reduces supply |
| Processors will create market pull (PepsiCo/McCain/SAI) | Expressed interest; agronomic validation | Medium–high — no contract/premium; exploratory only |
| The manual labour-saving model scales | Works for smallholders | Medium — advantage disappears under mechanisation / for larger farmers |
| Certification/carbon/NFT resolves a scaling constraint | Innovative concept | Medium — value proposition not tied to any binding constraint |
| The stated denominator (6–7M IGP households) is correct | EoI/Slides | Low–medium — disputed internally; affects ambition framing |

## 3.12 Evidence quality and confidence assessment

[Interpretation] Evidence quality is bimodal. On technology and farmer profitability it is strong and multi-source (RCT + peer-reviewed trials + external delivery evidence), though weakened by unreconciled numeric conflicts (Section 2.3) and by the RCT itself not being supplied. On scaling — delivery economics, actor incentives, sustained adoption, market and institutional demand — evidence is thin, borrowed, or absent.

Overall confidence — technical readiness: Well supported. Overall confidence — scaling-system readiness: Emerging to Insufficient. Net: a technically mature innovation not yet embedded in a viable, financed, demand-led, institutionally owned scaling system.

# 4. Stage-Gating Assessment

[Strategic Judgement] Components sit at different stages; they are assessed separately before an integrated judgement, per the diagnostic standard.

## 4.1 Component-level staging

| Component | Current stage | Evidence | Remaining gap |
| --- | --- | --- | --- |
| Core PZTM agronomy + manual delivery (DG/JEEViKA) | Transition to Scale | RCT; SRL~7; ~7,750 adopters | Delivery economics & sustained adoption unproven |
| Institutional embedding (Bihar extension) | Proof of Concept | Formal invitation; Road Map alignment | No MoU, budget line, or manual adoption |
| PPP / private-sector pathway | Proof of Concept | Processor interest; consortium 'started' | No contract, premium, or finalised consortium |
| Mechanization (zero-till planter) | Pre–Proof of Concept | Concept; partner identified | No prototype exists |
| Certification / NFT / carbon registry | Concept only | Idea articulated | No value proposition tied to a binding constraint |
| Farmer.Chat AI extension | Proof of Concept | Trained on PZTM manual | No cost-effectiveness vs video evidence |

## 4.2 Entry / exit criteria against the governing gate

### Proof of Concept → Transition to Scale (entry criteria for TTS)

- Technical efficacy under real conditions — MET (RCT, trials).

- A plausible, actor-specified scaling pathway — NOT MET (pathway undeclared; no actor business case).

- Evidence of institutional or market demand beyond the pilot — PARTIAL (invitation; exploratory processor interest).

### Transition to Scale → Active Scaling (exit criteria — what would justify advancement)

- A delivery agent operating at a known, fundable cost-per-sustained-adopter without donor top-up — NOT MET.

- A committed financing envelope (state budget line and/or private co-investment) — NOT MET.

- Demonstrated sustained (multi-season, unfacilitated) adoption — NOT MET.

- Resolved mulch-supply mechanism at block scale — NOT MET.

## 4.3 Integrated judgement

Current stage: Transition to Scale (driven by the mature core component; other components are earlier and should not be funded as if scaling).

Confidence: Moderate on the classification; the core is clearly past Proof of Concept but clearly not ready for Active Scaling.

Recommended gate: Transition to Scale with conditional, narrow funding — equivalent to Kohl's 'Targeted Bottleneck Support.' Fund one more year tied to proof points on delivery economics, actor business cases, institutional financing, and mulch supply. Do not fund certification, mechanization, or additional agronomic trials as scaling activities in this phase.

Justification: The innovation is more than a proof of concept — the agronomy is credible and institutional interest is real. It is not a proven scaling model, because business models, delivery economics, financing and ownership are undeveloped. The correct posture is conditional support, not uncritical acceleration.

### Preserved disagreement (A vs SC)

Analyst: the core bundle is technically 'scaling-ready' and could be classed as entering Active Scaling on technical grounds.

Strategy Coach: technical maturity is not scaling readiness; without a delivery-and-financing system the ceiling is Transition to Scale. The disagreement is exactly the lesson for CGIAR in Section 7.

# 5. Scaling Strategy Review

## 5.1 Strategic diagnosis

[Strategic Judgement] PZTM is a strong innovation carrying a weak scaling strategy. The strategy's defining problems are: no declared primary pathway; a 20+ activity portfolio with no prioritisation ('operationally busy without being structurally catalytic'); knowledge-push partners without delivery incentives; and a financing base that just lost its anchor (GIZ) with no committed successor. The re-framing that unlocks the strategy is to stop asking 'how do we deliver PZTM to more farmers?' and start asking 'who will own, deliver and pay for PZTM at scale after we leave, and what do they need to say yes?'

## 5.2 Priority actions (in sequence)

- Declare one primary pathway. Choose public-extension-led, PPP/processor-led, or community-enterprise-led as the spine for 2026, with the others as explicitly secondary. Base the choice on where an actor with an incentive can be shown to exist.

- Build actor-specific business/fiscal cases. For the state (cost per farmer of extension delivery vs budget), for JEEViKA/VRPs (what makes promotion worth their time), for a processor (does a PZTM premium pencil out), and for any private service provider (mulch/seed services).

- Convert the Bihar invitation into a costed MoU. A signed instrument with a budget line is the single highest-value 2026 milestone and the clearest additionality S4I can buy.

- Resolve one mulch-supply mechanism at block scale, but only once an actor with an incentive to run it is identified.

- Reconcile the evidence base into a single defensible fact sheet before external engagement (Section 2.3).

- Stop / defer: certification/NFT/carbon, mechanization prototyping, and additional agronomic trials as scaling activities this phase.

## 5.3 Owner-specific recommendations

- CIP / track leads: shift from delivery facilitator to scaling-system architect and evidence generator; treat coordination as a role to hand off, not to keep.

- S4I / AoW2: fund functions that de-risk the pathway (business cases, delivery economics, financing negotiation), not delivery volume; make funding conditional on proof points; commission the political-economy analysis.

- Digital Green: engage as a strategic advisor on prioritisation and cost-to-serve — 'where has DG advised against an approach?' — not only as a content producer.

- Bihar DoA/DoH: move from invitation to a costed commitment; define the extension mandate, training and budget that mainstreaming actually requires.

- AoW boundary note: AoW2 may diagnose enabling-environment and finance dependencies (mulch markets, subsidies, carbon) but should not claim to deliver AoW3/AoW4 functions; these should be framed as dependencies to be handed to the right actor, consistent with S4I role boundaries.

## 5.4 Adaptive management

[Interpretation] The existing cadence — quarterly check-ins, a Q3 mid-year review, GenderUp pre/post-season sessions — is a reasonable adaptive scaffold. Its weakness is the absence of decision rules. Reviews should carry explicit kill/pause/narrow/scale triggers tied to the learning experiments below, not just 'assess progress and adjust.' Krupnik's concentration-risk warning (the main intervention lands at year-end) means 2026 will yield little outcome evidence before decisions are due — so 2026 must be designed to test the pathway, not to maximise reach.

## 5.5 Institutionalization assessment

[Strategic Judgement] Institutionalisation is the stated primary pathway and the weakest-evidenced. A formal invitation is a beginning, not institutionalisation. Genuine institutionalisation requires PZTM in the extension manual, an officer-training mandate, a state budget line, and M&E the state itself runs. None exists. The risk Kohl repeatedly flags applies: large public programmes can convert scaling into target-driven activity expansion that distributes inputs without building durable adoption. S4I's role is to improve the quality of institutionalisation (rules, targeting, service standards), not to celebrate its announcement.

## 5.6 Sustainability assessment (strategy view)

[Interpretation] As configured, the strategy is not sustainable: it depends on donor facilitation that has already partly ended (GIZ), with successor financing and delivery ownership unresolved. Sustainability turns entirely on the weakest link — installing an actor with an incentive to deliver and pay. Every sustainability dimension in Section 3.10 improves if that one question is answered, and none improves much without it.

## 5.7 Learning experiments (turning unknowns into decisions)

[Recommendation] For each major uncertainty, the smallest practical experiment that would resolve it and the decision it would change:

| Uncertainty | Smallest experiment | Evidence required | Decision it changes |
| --- | --- | --- | --- |
| Who delivers, at what cost, without donor top-up? | Cost-to-serve study across DG-video vs Farmer.Chat vs govt-extension per sustained adopter, in a few blocks | $/sustained adopter by channel; who can bear it | Which primary pathway to back; whether any is fundable at scale |
| Will the state actually pay? | Negotiate a costed MoU / budget line with Bihar DoA in 2026 | Signed instrument with a rupee commitment | Whether the public pathway is real or aspirational |
| Is mulch a binding input constraint? | Straw-bank / paid-straw-service pilot in 2–3 blocks; measure straw price vs fodder value | Straw availability & price elasticity at block scale | Whether mulch scaling needs a market, a subsidy, or an alternative mulch |
| Is there market pull? | Secure one processor paid-sourcing pilot or price premium for PZTM potatoes | A signed offtake/premium term sheet | Whether the PPP/private pathway can lead |
| Does adoption persist unfacilitated? | Track the 2022 adopter cohort for continued use with facilitation withdrawn | Multi-season retention vs disadoption rate | Whether 'reach' figures represent durable adoption |
| Will the output market absorb expansion? | Rapid district-level potato market + cold-storage absorption analysis | Price response & storage capacity at target volume | Whether area-expansion targets are safe or will crash prices |

# 6. Richard Kohl Coaching Preparation Brief

## 6.1 Executive coaching summary

[Strategic Judgement] PZTM is one of the more agronomically convincing tracks Richard will see, and one of the least scaling-ready in its delivery and financing design. Expect him to affirm the science quickly and then spend the session almost entirely on the actor-and-business-case layer. Based on his DSR–Eastern-UP and comparable S4I assessments, his likely verdict is close to this report's: fund another year, conditionally and narrowly, tied to proof points; distinguish technical maturity from scaling readiness; and insist the team convert an activity map into an actor-driven scaling system with post-donor ownership. The team should walk in having already done the prioritisation and business-case thinking, so the session can go deeper than diagnosis.

## 6.2 Five questions Richard is most likely to ask

- Who delivers PZTM at scale, and what is their business or fiscal case — who earns, who pays, who bears the risk, and who continues after S4I and GIZ funding end?

- You have ~7,750 adopters after ~4 years of facilitation. What specifically changes to reach 35,000–50,000 — and is that reach, or high-fidelity sustained adoption?

- Is rice straw actually available at scale given its value as livestock feed and the spread of combine harvesting — and if not, who has the incentive to build a straw-supply market?

- Which single scaling pathway are you betting on, and what evidence shows its enabling conditions are achievable at state scale?

- What is the farmer's output-market story — potato demand versus rice, price, and cold-storage absorption — if tens of thousands more households grow potatoes?

## 6.3 Five assumptions Richard is most likely to challenge

- That farmer-level profitability (the RCT) implies the innovation will scale through institutions and markets.

- That public extension will carry delivery at state scale (his own two-pager: MinAg/NARES systems are under-resourced and default to one-way dissemination).

- That rice-straw availability 'will not be a key challenge during the current scaling phase' (the EoI's explicit assumption; IPSR itself rated straw readiness 'low').

- That the manual, labour-saving model scales — its advantage disappears under mechanisation and for larger farmers.

- That certification / carbon / NFTs resolve a binding scaling constraint rather than adding transaction cost.

## 6.4 Three areas where the team is likely overestimating readiness

- Institutional embedding: an invitation to submit a proposal is being treated as government adoption. No MoU, budget line or manual integration exists.

- Private-sector / PPP pull: processor interest is exploratory; there is no sourcing contract, price premium, or finalised consortium.

- Deep-scaling and gender outcomes at scale: the team concedes 2026 outcomes will be assumed, not measured; and profitability raises a real gender-capture risk (men taking over a lucrative enterprise) that monitoring has not yet resolved.

## 6.5 Three strengths Richard is likely to recognize

- Genuine problem–solution fit with rigorous farmer evidence: a real systems problem (degrading rice-fallow systems, residue burning, labour and water stress) met by a validated, RCT-backed, profitable practice.

- A real institutional anchor and government demand signal: the Bihar Road Map alignment and the formal invitation give a better starting point than many tracks.

- A trusted, gender-responsive last-mile delivery asset: the Digital Green + JEEViKA SHG network is a genuine channel to marginalised women farmers — an asset most tracks lack.

## 6.6 Evidence the team should have available

- A reconciled one-page fact sheet (single agreed figures for gross margin, yield, cost, adopters, targets).

- The Bihar RCT (methods + results) and the pest/disease study, even if pre-publication.

- A first-cut actor business/fiscal case for the chosen primary pathway.

- Current status of the Bihar proposal / any draft MoU and the state financing timeline.

- What GIZ closure removed (people, budget, activities) and what, if anything, replaces it.

## 6.7 Evidence currently missing

- Delivery cost-per-sustained-adopter by channel; sustained/unfacilitated adoption and disadoption data.

- Actor-specific business cases; output-market and cold-storage absorption analysis.

- A political-economy / stakeholder analysis; the S4I grant amount and budget.

## 6.8 Recommended 90-minute coaching agenda

| Time | Focus | Intended output |
| --- | --- | --- |
| 0–10 min | Team frames the one binding constraint it now believes is primary (pre-work) | Shared problem statement |
| 10–30 min | Delivery & incentives: who delivers, earns, pays, continues | Draft actor map with incentives named |
| 30–50 min | Pathway selection: pick ONE primary pathway; test enabling conditions | A declared primary pathway + secondary |
| 50–65 min | Financing & institutionalisation after GIZ: MoU, state budget, successor funding | Financing/ownership plan with named owners |
| 65–80 min | Proof points & decision rules for 2026 (learning experiments) | 3–4 proof points with kill/pause/scale triggers |
| 80–90 min | What to stop doing; additionality of S4I | A 'stop list' and a one-line additionality statement |

## 6.9 Three conversations to have internally before coaching

- Prioritisation: agree the one primary pathway and, harder, agree what to stop doing from the 20+ activity list.

- Evidence integrity: reconcile the conflicting numbers into one fact base the team will defend under questioning.

- Post-GIZ ownership: decide who is meant to own, deliver and pay for PZTM after the bilateral's closure — and be honest about whether that actor has yet said yes.

## 6.10 If Richard remembered only one thing six months later

“PZTM has proven the agronomy and the farmer case; it has not yet proven that anyone other than CGIAR will deliver and pay for it at scale. The whole track hinges on converting a facilitated pilot into an actor-owned delivery-and-financing system.”

# 7. Operating System Improvement Recommendations

[Recommendation] These recommendations concern the Scaling Intelligence Operating System itself, and are deliberately separated from the recommendations for the PZTM track (Sections 4–6). Each is prompted by a friction encountered while assessing this track.

## 7.1 Scaling Knowledge Standard

- Require a single canonical fact sheet per track (one agreed value per headline metric). The PZTM assessment surfaced four adopter counts and a 16%-vs-60% gross-margin conflict — a knowledge-integrity failure that a mandatory reconciliation step would prevent.

- Add a mandatory provenance tag for AI-generated content (the EoI's responsible-scaling section was LLM-generated); and a standing 'cited-but-unsupplied' register so central evidence like the RCT cannot be assumed present.

## 7.2 Scaling Intelligence Standard

- Make the four nested adoption metrics (reach / trial / effective / sustained) a required field, to stop 'households reached' standing in for scaling.

- Make the Additionality Test and an actor-specific business-case template mandatory sections whenever a track builds on an existing platform or programme.

## 7.3 Scaling Strategy Standard

- Require a single declared primary pathway plus an explicit 'stop list.' The recurring failure across tracks (PZTM, DSR) is undifferentiated multi-pathway activity portfolios.

- Add a required 'who pays / who continues after donor support' field to every pathway.

## 7.4 Weakest-link reasoning

- Institutionalise the anti-legibility check as a required step — force the assessor to name the most legible constraint and then ask whether a less-legible, more-upstream one dominates. This is what separated 'mulch' (legible) from 'delivery incentives' (binding) in this case.

- Require explicit upstream/downstream classification and a 'who performs / who pays / who continues' line for each candidate constraint.

## 7.5 Stage-gating

- Require component-level staging before an integrated gate; PZTM ranges from 'Active-Scaling-ready agronomy' to 'concept-only certification' inside one track, and a single gate would have masked that.

- Adopt Kohl's 'Targeted Bottleneck Support' as a first-class gate option distinct from Active Scaling.

## 7.6 Coaching preparation

- Template this coaching brief (Sections 6.1–6.10) as a reusable pre-coaching artifact; the likely-questions / challenged-assumptions / overestimated-readiness structure transfers directly across tracks.

## 7.7 Evidence handling & repository structure

- Enforce the document-assertion vs observed-evidence distinction in the Librarian intake (the EoI asserts benefits that trials only partially observe).

- Store discipline disagreements as first-class objects rather than resolving them; the L/A/SC divergence on the weakest link is itself reusable intelligence.

- Recommend Knowledge Cards, an Insight Page ('technical maturity is not scaling readiness — a recurring CGIAR pattern'), and a Heuristic Page ('legible constraints crowd out binding ones') for the Librarian to create for human review.

Note on limits of this assessment. This is a blind, document-based assessment of five supplied sources. It did not confirm readiness for scaling; it asked what is proven, what remains assumption, what evidence would justify advancement, what the most upstream constraint is, and what smallest experiment would most improve the odds of successful scaling. Field verification with farmers, non-adopters, extension officers, JEEViKA VRPs, and prospective processors would materially change confidence and should precede any scaling decision.